## Sheet1
PGT - Tourism Promotion Update (28 Oct 2020)
Details | Date | Budget | Remark
Domestic
EPY Roadshow in KL | March | 180000 | Completed
Media Campaign - Penang Travel Deals with Sojern | July-Sept | 42000 | Completed
Media Campaign - Penang Travel Deals with Astro Radio | Sept-Oct | 250000 | Completed
MICA Penang Foliday Consortium Campaign | Aug-Sept | 31000 | Completed. Packages will be continue for sale until 31 December 2020
Online MATTA Fair | Sept | 35000 | Completed
MCTA Penang Packages Recovey Campaign | July-Dec | 300000 | To be extended until 31 Dec 2020
Domestic Campaign with MHholidays | Aug | 14000 | Completed | Domestic Campaign RM100,000
Media Campaign - Penang Travel Deals with Sojern | Oct-Dec | 65000 | On-going
Domestic Campaign with Klook | Mid Nov 2020 - Feb 2021 | 600000 | Pending MOU date (preferably mid Nov)
Domestic Campaign with Booking.com & Shopback | Dec 2020 - Feb 2021 | 600000 | Commence Dec
Domestic Campaign with AirAsia | Oct-Dec | 550000 | On-going
Domestic Campaign with Expedia & Malaysia Airlines | Mid Nov 2020 - Jan 2021 | 150000 | Commence mid Nov | Domestic Campaign RM300,000 + RM10,000 from Europe Tactical Campaign
Domestic Media Campaign with Firefly | Dec 2020 - Feb 2021 | 80000 | Billboards in Johor, Kota Kinabalu and Kuching
Domestic Campaign with Malaysiakini | Nov-Dec | 80000 | Penang #24hours shooting on 17-18 November 2020
Regional Countries
ATF Brunei | Jan | 230000 | Completed
Hong Kong Tactical Campaign | Dec | 150000 | Celebrity Live Campaign | RM50,000 from Taiwan
Singapore Tacticcal Campaign | Dec | 100000 | AirAsia / Penang Food
China Roadshow with Qingdao Airlines & Marketing Campaign (Ctrip & Tuniu) | 2021 | 1000000 | On hold until 2021
Thailand Tactical Campaign | Dec 2020 - 2021 | 150000 | Content marketing
Taiwan Tactical Campaign | Dec 2020 - 2021 | 210000 | Content marketing with airlines | Reduce budget for Indonesia (RM20,000), Hong Kong (RM50,000)
Media Campaign with Airlines in Indonesia | Dec 2020 - Feb 2021 | 120000 | To advertise in billboards | RM20,000 from Europe
Vietnam Tactical Campaign | Dec 2020 - Feb 2021 | 90000 | To work with AirAsia
Medium-Long Haul Countries
Middle East - Emirates Holidays Campaign | March | 6200 | Completed
ITB Berlin | March | 35000 | Completed
Japan Tactical Campaign | Dec 2020 - 2021 | 150000 | Content Marketing
South Korea Tactical Campaign with Airlines and Agents | Dec 2020 - 2021 | 150000 | Content Marketing | RM50,000 from Europe
Australia Tactical Promotion - OTA/Wholsaler | 2021 | 100000 | On hold until 2021
Content Marketing in Europe | Dec 2020 - March 2021 | 100000 | Content Marketing | Budget from WTM London
Europe Tactical Campaign - Airlines/Wholesaler | Dec | 250000 | For video productions / gifts / online mini games | Reduce budget to Firefly (RM10,000), Korea (RM50,000)
Middle East - Tactical Campaign B2B (Hotel Fee) | 2021 | 150000 | On hold until 2021
Others
Wedding Tourism - Malaysia/Asia | July-Dec | 40000 | On-going