## PTMP
PENANG GLOBAL TOURISM SDN BHD
PENANG TOURISM MASTER PLAN 2019-2020
Project : | Penang Tourism Master Plan
File Ref :
PERIOD : | 2019 - 2021
Officer Incharged : |  | Darren Ng
Approval : |  | YB Yeoh Soon Hin
Estimated Cost for the project : |  | 600000
Actual Cost for the project |  | 441938.5
Details of Expenditure for the project :
PV number | Description |  | Payable to | Budgeted Amount (RM) | Actual Amount (RM) | Remarks
V2019/587 | Lunch/Dinner Hosting-24/06/19 |  | Jazz Hotel Penang Malaysia |  | 6000
V2019/616 | First Payment - 20% of RM496,730 |  | YZD Planning & Consult |  | 93722.64 |  | PTS TRAVEL & TOURS SDN BHD
V2019/616 | First payment SST 6% |  | YZD Planning & Consult |  | 5623.36 |  | Pts Travel & Tours Sdn Bhd
V2019/622 | Video Record-Ptmp Sign Ceremony 24/06/19 |  | Image Farm Productions Sdn Bhd |  | 3000
V2019/650 | Host Service-MOU Sign Ceremony 24/06/19 |  | Carolyn Ooi Ai Choo |  | 600
V2019/847 | Second Payment - 20% of RM496,730 |  | YZD Planning & Consult |  | 93722.64
V2019/847 | Second Payment 6% SST |  | YZD Planning & Consult |  | 5623.36
V2019/975 | Third Payment - 30% of RM496,730 |  | YZD Planning & Consult |  | 140583.96
V2019/975 | Third Payment 6% SST |  | YZD Planning & Consult |  | 8435.04
V2020/189 | Forth Payment - 15% of RM496,730 |  | YZD Planning & Consult |  | 70291.98
V2020/189 | Forth Payment 6% SST |  | YZD Planning & Consult |  | 4217.52
V2020/279 | Half Day Meeting Package On 13/2/20 |  | YZD Planning & Consult |  | 5300
V2020/279 | 6% SST |  | YZD Planning & Consult |  | 318
V2020/566 | PTMP Town Hall Session 12/9(50Pax) |  | Boustead Weld Quay Sdn Bhd |  | 4500
| Total Expenditure for the project |  |  | 600000 | 441938.5
Remarks :
Final payment of 15% which amounting to RM74,509.50 reamined unpaid from 2020.