## GST-01
GST Issues Log | [7 empty] | STATUS
[10 empty] | Not yet started | Not Yet Started
|  |  | 02 | Budgeting and Resource Requirement for GST Implementation |  |  |  |  | In Progress | In Progress | In Progree
[10 empty] | Done | Done
PIC: | Michelle
Work Plan |  | Target Date | Completed Date | Info collected / summary of findings | Policy and Procedures (P&P) Changes (Yes /No) | Description of P&P Changes | Tool / System Changes (Yes / No) | Description of Tool / System Changes | Status / Remarks
1 | Identify capital expenditure to be made close to GST Implentation date | 2014-08-29 | 2014-08-28
| - Upgrading system |  |  | - PC system to be upgraded (if needed) & re-install UBS system | No | N/A | Yes | Upgrading/Change new PC | In process
| - Changes to stationary comply with GST |  |  | - Payment voucher (to add a coloum for GST tax coding) | Yes | To analyse the code in Payment voucher | Yes | To add a column in Payment Voucher for tax coding | Done
| - Training staff |  |  | - To attend UBS training | No | N/A | No | N/A
| - software upgrades |  |  | UBS version is now upgraded to V9.9.0.3. | No | N/A | Yes | Will be upgraded to GST compliance | In Process
2 | Plan and document a budget to fund necessary expenditure | 2014-08-29 | 2014-08-28
| - Upgrading system |  |  | - Estimated RM2,500 for new PC | No | N/A | Yes | - UBS re-installation and configureation charges TBA | TBA
| - Training staff |  |  | - Course fee TBA | No | N/A | No | N/A | N/A
| - software upgrades |  |  | Software upgraded for 2 pc - RM150.00 | No | N/A | No | Will be upgraded to GST compliance | In Process
3 | Devise a plan outlining the timing of changes (and expenditure) required | 2014-08-29 | 2014-08-28 | Targeted UBS to be upgraded in October | No | N/A | Yes | UBS system will be upgraded to GST compliance | October
4 | Review and assess the resource requirements for GST to undertake the following :- | 2014-08-29 | 2014-08-28
a. | Act as a contact point for customs requires |  |  | Currently no body | Yes | Acc exe to handle GST filing & submission | Yes | Additonal role for Acc Exe
b. | Undertake internal GST audit/reviews of systems and processes to ensure compliance |  |  | Currently no body | Yes | Acc. Exe to exercise GST submission and filing, MD/GM to review and sign off | Yes | Additonal role for Acc Exe
c. | Process and maintain invoices to substantiate input tax claims; |  |  | Currently no tax invoice, All invoice file with payment voucher | Yes | To file invoice differently according to input tax and output tax | Yes | Additonal role for Acc Exe
d. | Prepare, complete and submit the monthly GST including reviewing, verifying and reconciling all data captured |  |  | Currently no body | Yes | Acc. Exe to exercise GST submission and filing, MD/GM to review and sign off | Yes | Additonal role for Acc Exe
5 | Management to determine the resources needed to ensure your GST requirement is met | 2014-08-29 | 2014-08-28 | Currently no body | Yes | expand role to include compilation & submission of gst | Yes | Additonal role for Acc Exe
6 | Communicate changes to employees | 2014-08-29 | 2014-08-28

## GST-01 Appendix 1
Work Flow
Received Invoice from Supplier/Vendor
Matching Invoice with Purchase Order & Purchase Requisition/Memo
Invoice verified , checked and signed by requisitor
Invoice approved and signed by Managing Director
Invoice placed on hold. Department notified of required action
Action taken, Issued resolved?
Invoice placed in payment queue
Payment processed
NO
YES
NO
YES

## GST-01 Appendix 2
Work Flow
Received Invoice from Supplier/Vendor
Matching Invoice with Purchase Order & Purchase Requisition/Memo
Invoice verified , checked and signed by requisitor
Invoice approved and signed by Managing Director
Invoice placed on hold. Department notified of required action
Action taken, Issued resolved?
Invoice placed in payment queue
Payment processed
NO
YES
NO
YES
To analyse GST Tax Coding for ITC
To check invoice meets requirement for ITC purpose
Return to Supplier/Vendor
YES
NO

## GST-01 Appendix 3
Penang Global Tourism Sdn Bhd (Co. No. 50689-X)
(formerly known as DCT Consultancy Services Sdn Bhd)
No. 8B, (First Floor) The Whiteaways Arcade, Lebuh Pantai, 10300 Penang
Tel: 604-264 3456 Fax : 604-264 3455
To: |  |  | PAYMENT VOUCHER
Voucher No. :
Date :
Bank :
Cheque No. :
INVOICE DATE | INVOICE NO | PARTICULARS |  | AMOUNT (RM)
0
TOTAL :RINGGIT
Prepared by: |  |  | CIMB Bizchannel Transaction No.
GST Tax Code
Approved by: |  |  | Received by:
Managing Director |  |  | I/C No:
Date:
Kindly acknowledge receipt.
Thank you.

## GST-04
GST Issues Log | [7 empty] | STATUS
[10 empty] | Not yet started | Not Yet Started
|  |  | 04 | Preferred Vendor Management |  |  |  |  | Not yet started | In Progress | In Progree
[10 empty] | Done | Done
PIC: Michelle
Work Plan |  | Target Date | Completed Date | Info collected / summary of findings | Policy and Procedures (P&P) Changes (Yes /No) | Description of P&P Changes | Tool / System Changes (Yes / No) | Description of Tool / System Changes | Status / Remarks
1 | Analyse existing supplies/vendors if they are potiental gst registrant | 2014-09-05 | 2014-09-05 | Prepare a vendor listing and analyse | Yes | To decide if want to continue with non register vendors | Yes | To mannually keep track vendor for GST or non GST
2 | Determine if management would establish policy on preferred vendor program or continue engaging non register vendors | 2014-09-05 | 2014-09-05 | Most of the suppliers/vendor are potential gst registrant Some of the are uncertain | Yes | To decide if want to continue with register or non register vendor (subject to PGT's future outcome on whether to register with gst) | Yes | To mannually keep track vendor for GST or non GST
3 | If management decides to implement the programme, communication policy to vendors and develop procedures to track GST status of vendors | 2014-09-05 | 2014-09-05 | To follow up & keep track with supplies/vendors who are potential gst registrant and collect gst documentation from them | Yes | To filing related GST documentation provided by suppliers | No | N/A
4 | If management decides to continue with the current practices and engage non-registered vendors, ensure the GST status of the vendor and the transaction are tracked seperately | 2014-09-05 | 2014-09-05 | Management to decide whether to continue with non register supplier. PGT will have to engage with non register supplier if the supplies are unique. | No | N/A | No | N/A
5 | Update the changes to processes and systems to enable tracking of vendors and their transactions | 2014-09-05 | 2014-09-05 | To decide on the tax coding exercise, base on account or transaction approach | Yes | To analyse the each of every expenses base on tax coding approach | Yes | UBS account code might be affected
6 | Educate staff on the updated processes and system changes | 2014-09-05 | 2014-09-05 | Currently no body | Yes | Additional task for accounts executive | No | N/A
7 | Communicate with procurement/vendors on PGT's policy on preferred vendor scheme | 2014-09-05 | 2014-09-05 | Currently no body | Yes | All staffs to involve | No | N/A

## GST-04 Appendix 1
GST 04 - Preferred Vendor Management
No. | (1) Name of vendors & suppliers Please provide the name of vendors & suppliers of PGT | (2) Is the vendors/suppliers is/will be GST registrant? Please select from drop down menu | (3) Further action Please select from drop down menu | Drop-down menu data
1 | ALUNAN MATRIK SDN BHD | Yes | To get GST registration document from supplier | Column (2) | Column (3)
2 | ASIA ITINERARY TRAVEL & TOURS S/B | Yes | To get GST registration document from supplier | Yes | Discuss with vendor/supplier for voluntary registration
3 | ASTRO RADIO SDN BHD | Yes | To get GST registration document from supplier | No | To terminate any agreement with the vendor/supplier
4 | AVION HOLIDAYS SDN BHD | Yes | To get GST registration document from supplier | Uncertain | To follow up with supplier if they will register
5 | BAGAN EIGHTEEN SDN BHD | Yes | To get GST registration document from supplier |  | To get GST registration document from supplier
6 | BENFONT ENTERPRISE | Uncertain | To follow up with supplier if they will register
7 | BON TON SDN BHD | Yes | To get GST registration document from supplier
8 | BOUSTED WELD QUAY SDN BHD | Yes | To get GST registration document from supplier
9 | BRANDING AT HEKTY SDN BHD | Uncertain | To follow up with supplier if they will register
10 | CAHAYA UTARA SDN BHD | Yes | To get GST registration document from supplier
11 | CAPITAL ONE LEISURE SDN BHD | Yes | To get GST registration document from supplier
12 | CHINA SOUTHERN AIRLINES | Yes | To get GST registration document from supplier
13 | CHING XING SPORTS AND CULTURAL CENTRE | Uncertain | To follow up with supplier if they will register
14 | CLARITY PUBLISHING SDN BHD | Uncertain | To follow up with supplier if they will register
15 | CORPORATENET SDN BHD | Yes | To get GST registration document from supplier
16 | DESIGN ARK SDN BHD | Yes | To get GST registration document from supplier
17 | DESIGN FURNITURE STATION | No | Discuss with vendor/supplier for voluntary registration
18 | DHL EXPRESS (MALAYSIA) SDN BHD | Yes | To get GST registration document from supplier
19 | DREAM RIVER VISON ENTERPRISE | Uncertain | To follow up with supplier if they will register
20 | DSOP OFFICE SYSTEM & SUPPLIES SDN BHD | Yes | To get GST registration document from supplier
21 | EASTERN & ORIENTAL HOTEL SDN BHD | Yes | To get GST registration document from supplier
22 | EASTIN HOTEL PENANG | Yes | To get GST registration document from supplier
23 | EDITORIAL ASSOCIATES | No | Discuss with vendor/supplier for voluntary registration
24 | ELITE TRANSLATIONS ASIA (M) SDN BHD | Uncertain | To follow up with supplier if they will register
25 | EMANON SDN BHD | Yes | To get GST registration document from supplier
26 | EMSOFT TRADING | Uncertain | To follow up with supplier if they will register
27 | ERNST & YOUNG TAX CONSULTANTS SDN BHD | Yes | To get GST registration document from supplier
28 | FOUR POINTS BY SHERATON PENANG | Yes | To get GST registration document from supplier
29 | FREEDOM GETAWAY ADVENTURES | Uncertain | To follow up with supplier if they will register
30 | FTZ TRAVEL & TOURS SDN BHD | Uncertain | To follow up with supplier if they will register
31 | FUJI XEROX ASIA PACIFIC PTE LTD | Uncertain | To follow up with supplier if they will register
32 | GO INTERNATIONAL GROUP SDN BHD | Uncertain | To follow up with supplier if they will register
33 | GEORGE TOWN WORLD HERITAGE INCORPORATED | Uncertain | To follow up with supplier if they will register
34 | HARPERS TRAVEL (M) SDN BHD | Uncertain | To follow up with supplier if they will register
35 | HOLIDAY TOURS & TRAVEL SDN BHD | Yes | To get GST registration document from supplier
36 | IMAGE FARM PRODUCTIONS SDN BHD | Yes | To get GST registration document from supplier
37 | IMPRESS LED ADVERTISE SDN BHD | Uncertain | To follow up with supplier if they will register
38 | ISLAMIC TOURISM CENTRE | Uncertain | To follow up with supplier if they will register
39 | JAYKODI RESOURCES | Uncertain | To follow up with supplier if they will register
40 | LA VINTAGE DESING | Uncertain | To follow up with supplier if they will register
41 | LAM AH COMPANY SDN BERHAD | Yes | To get GST registration document from supplier
42 | LEE VIDEO PRODUCTIONS SDN BHD | Uncertain | To follow up with supplier if they will register
43 | LEGION PARKING (M) SDN BHD | Uncertain | To follow up with supplier if they will register
44 | LIANG PRINTING SERVICES | Uncertain | To follow up with supplier if they will register
45 | MAGICPRINT SOLUTIONS | Uncertain | To follow up with supplier if they will register
46 | MERU UTAMA SDN BHD | Yes | To get GST registration document from supplier
47 | MSCB SYSTEM (PG) SDN BHD | Yes | To get GST registration document from supplier
48 | OMEGA SPARKLES SDN BHD | Uncertain | To follow up with supplier if they will register
49 | P.P. SETIA ENTERPRISE | Uncertain | To follow up with supplier if they will register
50 | PDC PREMIER HOLDINGS SDN BHD | Yes | To get GST registration document from supplier
51 | PENANG HERITAGE TRUST | Uncertain | To follow up with supplier if they will register
52 | PERBADANAN PEMBANGUNAN PULAU PINANG | Yes | To get GST registration document from supplier
53 | PERSATUAN PENDIDIKAN SENI PP | Uncertain | To follow up with supplier if they will register
54 | PEWTER ART TROPHY MANUFACTURES SDN BHD | Uncertain | To follow up with supplier if they will register
55 | PGCC SALES & SERVICES SDN BHD | Yes | To get GST registration document from supplier
56 | PPB GROUP BERHAD | Yes | To get GST registration document from supplier
57 | PTS TRAVEL & TOURS SDN BHD | Uncertain | To follow up with supplier if they will register
58 | R.KANESAN | Uncertain | To follow up with supplier if they will register
59 | RAPID BUS SDN BHD | Uncertain | To follow up with supplier if they will register
60 | SIN HIN BANNERS & SCRILLS SERVICES | Uncertain | To follow up with supplier if they will register
61 | STAR PUBLICATIONS (M) BERHAD | Yes | To get GST registration document from supplier
62 | STRAITS INDIGO SDN BHD | Uncertain | To follow up with supplier if they will register
63 | SYARIKAT PERCETAKAN IRISAN SDN BHD | Uncertain | To follow up with supplier if they will register
64 | TELEKOM MALAYSIA BERHAD | Yes | To get GST registration document from supplier
65 | TENAGA NASIONAL BERHAD | Yes | To get GST registration document from supplier
66 | THAI AIRWAYS INTERNATIONAL PUBLIC CO LTD | Yes | To get GST registration document from supplier
67 | THE PHOENIX PRESS SDN BHD | Uncertain | To follow up with supplier if they will register
68 | THE WELLPACK INS. SUPPLIES S/B | Uncertain | To follow up with supplier if they will register
69 | TNT EXPRESS WORLDWIDE (M) SDN BHD | Uncertain | To follow up with supplier if they will register
70 | TONG YAN TRAVEL & TOURS SDN BHD | Uncertain | To follow up with supplier if they will register
71 | TOONG LI STATIONERY & SUPPLY | Uncertain | To follow up with supplier if they will register
72 | TOP ONE DIGITAL SHOP | Uncertain | To follow up with supplier if they will register
73 | TOUR & INCENTIVE TRAVEL SDN BHD | Yes | To get GST registration document from supplier
74 | ULYSSESS WORDSTATION | Uncertain | To follow up with supplier if they will register
75 | UNI. ASIA GENERAL INSURANCE BERHAD | Yes | To get GST registration document from supplier
76 | USAINS HOLDING SDN BHD | Yes | To get GST registration document from supplier
77 | VCREATE SDN BHD | Uncertain | To follow up with supplier if they will register
78 | WEB ASP SDN BHD | Uncertain | To follow up with supplier if they will register
79 | WINSOME AIR-CONDITION ENGINEERING | Uncertain | To follow up with supplier if they will register
80 | WT LIM FOOD PRODUCTS SDN BHD | Uncertain | To follow up with supplier if they will register
81 | YNOT MUSIC STUDIO | Uncertain | To follow up with supplier if they will register
82 | YTL COMMUNICATIONS SDN BHD | Yes | To get GST registration document from supplier

## GST-04 Appendix 2
No. | SUPPLIER/VENDOR | Potential GST Registrant
|  | Yes | No | Uncertain | Estimate
1 | ALUNAN MATRIK SDN BHD | ü
2 | ASIA ITINERARY TRAVEL & TOURS S/B | ü
3 | ASTRO RADIO SDN BHD | ü |  |  | *
4 | AVION HOLIDAYS SDN BHD | ü |  |  | *
5 | BAGAN EIGHTEEN SDN BHD | ü |  |  | *
6 | BENFONT ENTERPRISE |  |  | ü
7 | BON TON SDN BHD | ü |  |  | *
8 | BOUSTED WELD QUAY SDN BHD | ü |  |  | *
9 | BRANDING AT HEKTY SDN BHD |  |  | ü
10 | CAHAYA UTARA SDN BHD | ü |  |  | *
11 | CAPITAL ONE LEISURE SDN BHD | ü |  |  | *
12 | CHINA SOUTHERN AIRLINES | ü |  |  | *
13 | CHING XING SPORTS AND CULTURAL CENTRE |  |  | ü
14 | CLARITY PUBLISHING SDN BHD |  |  | ü
15 | CORPORATENET SDN BHD | ü
16 | DESIGN ARK SDN BHD | ü |  |  | *
17 | DESIGN FURNITURE STATION |  | ü
18 | DHL EXPRESS (MALAYSIA) SDN BHD | ü
19 | DREAM RIVER VISON ENTERPRISE |  |  | ü
20 | DSOP OFFICE SYSTEM & SUPPLIES SDN BHD | ü
21 | EASTERN & ORIENTAL HOTEL SDN BHD | ü
22 | EASTIN HOTEL PENANG | ü
23 | EDITORIAL ASSOCIATES |  | ü
24 | ELITE TRANSLATIONS ASIA (M) SDN BHD |  |  | ü
25 | EMANON SDN BHD | ü |  |  | *
26 | EMSOFT TRADING |  |  | ü
27 | ERNST & YOUNG TAX CONSULTANTS SDN BHD | ü
28 | FOUR POINTS BY SHERATON PENANG | ü
29 | FREEDOM GETAWAY ADVENTURES |  |  | ü
30 | FTZ TRAVEL & TOURS SDN BHD |  |  | ü
31 | FUJI XEROX ASIA PACIFIC PTE LTD |  |  | ü
32 | GO INTERNATIONAL GROUP SDN BHD |  |  | ü
33 | GEORGE TOWN WORLD HERITAGE INCORPORATED |  |  | ü
34 | HARPERS TRAVEL (M) SDN BHD |  |  | ü
35 | HOLIDAY TOURS & TRAVEL SDN BHD | ü
36 | IMAGE FARM PRODUCTIONS SDN BHD | ü |  |  | *
37 | IMPRESS LED ADVERTISE SDN BHD |  |  | ü
38 | ISLAMIC TOURISM CENTRE |  |  | ü
39 | JAYKODI RESOURCES |  |  | ü
40 | LA VINTAGE DESING |  |  | ü
41 | LAM AH COMPANY SDN BERHAD | ü
42 | LEE VIDEO PRODUCTIONS SDN BHD |  |  | ü
43 | LEGION PARKING (M) SDN BHD |  |  | ü
44 | LIANG PRINTING SERVICES |  |  | ü
45 | MAGICPRINT SOLUTIONS |  |  | ü
46 | MERU UTAMA SDN BHD | ü
47 | MSCB SYSTEM (PG) SDN BHD | ü
48 | OMEGA SPARKLES SDN BHD |  |  | ü
49 | P.P. SETIA ENTERPRISE |  |  | ü
50 | PDC PREMIER HOLDINGS SDN BHD | ü
51 | PENANG HERITAGE TRUST |  |  | ü
52 | PERBADANAN PEMBANGUNAN PULAU PINANG | ü
53 | PERSATUAN PENDIDIKAN SENI PP |  |  | ü
54 | PEWTER ART TROPHY MANUFACTURES SDN BHD |  |  | ü
55 | PGCC SALES & SERVICES SDN BHD | ü
56 | PPB GROUP BERHAD | ü |  |  | *
57 | PTS TRAVEL & TOURS SDN BHD |  |  | ü
58 | R.KANESAN |  |  | ü
59 | RAPID BUS SDN BHD |  |  | ü
60 | SIN HIN BANNERS & SCRILLS SERVICES |  |  | ü
61 | STAR PUBLICATIONS (M) BERHAD | ü |  |  | *
62 | STRAITS INDIGO SDN BHD |  |  | ü
63 | SYARIKAT PERCETAKAN IRISAN SDN BHD |  |  | ü
64 | TELEKOM MALAYSIA BERHAD | ü
65 | TENAGA NASIONAL BERHAD | ü
66 | THAI AIRWAYS INTERNATIONAL PUBLIC CO LTD | ü
67 | THE PHOENIX PRESS SDN BHD |  |  | ü
68 | THE WELLPACK INS. SUPPLIES S/B |  |  | ü
69 | TNT EXPRESS WORLDWIDE (M) SDN BHD |  |  | ü
70 | TONG YAN TRAVEL & TOURS SDN BHD |  |  | ü
71 | TOONG LI STATIONERY & SUPPLY |  |  | ü
72 | TOP ONE DIGITAL SHOP |  |  | ü
73 | TOUR & INCENTIVE TRAVEL SDN BHD | ü
74 | ULYSSESS WORDSTATION |  |  | ü
75 | UNI. ASIA GENERAL INSURANCE BERHAD | ü |  |  | *
76 | USAINS HOLDING SDN BHD | ü |  |  | *
77 | VCREATE SDN BHD |  |  | ü
78 | WEB ASP SDN BHD |  |  | ü
79 | WINSOME AIR-CONDITION ENGINEERING |  |  | ü
80 | WT LIM FOOD PRODUCTS SDN BHD |  |  | ü
81 | YNOT MUSIC STUDIO |  |  | ü
82 | YTL COMMUNICATIONS SDN BHD | ü |  |  | *

## GST-06
GST Issues Log | [7 empty] | STATUS
[10 empty] | Not yet started | Not Yet Started
|  |  | 06 | Price Rebalancing |  |  |  |  | Not yet started | In Progress | In Progree
[10 empty] | Done | Done
PIC: Michelle
Work Plan |  | Target Date | Completed Date | Info collected / summary of findings | Policy and Procedures (P&P) Changes (Yes /No) | Description of P&P Changes | Tool / System Changes (Yes / No) | Description of Tool / System Changes | Status / Remarks
1 | Determine transactions in which the implementation of GST may result in material savings/increase in costs | 2014-09-05 | 2014-09-05 | - Cash flow may affected in circumtances where PGT has short credit periods from supplier, this may result in PGT needing extra finances to purchase supplies | Yes | - PGT - 6% additional cost to be incurred in PGT expenses (Subject to PGT's future outcome, if the grant is exempted, not entitle for ITC) | Yes
2 | Asses impact to cost and pricing of PGT services with the introduction of GST and the repeal of sales and service tax | 2014-09-05 | 2014-09-05 | - Currently most of the suppliers/vendors does not charge SST/GST - Selling price of merchandise in TIC will be increased when GST implement | Yes | - To collect 6% of GST from customers @ TIC /PGT | Yes | - TIC's Point of Sales System to be add in a module for GST - UBS system to be upgraded to GST compliance
3 | Identify related documents to be updated / amended to quote price with GST inclusive | 2014-09-05 | 2014-09-05 | - Currently all pricing quoted/sold are excluded 6% | Yes | - To change quotation format - To added in 6% in the quotation - - Management to decide the open market value for sponsorship in return | Yes | To keep track and filing of quotation GST or non GST inclusive
4 | Determine and implement process and system change required | 2014-09-05 | 2014-09-05 | - Price quoted via email from manager | Yes | - To change the process of quotation - Account department to prepare the quotation | No | N/A
5 | Ensure that pricing decisions based on these transaction are justifiable by PGT | 2014-09-05 | 2014-09-05 | - Pricing of merchandise will be based on 6% from supplier | Yes | - To added 6% for every merchandise (If PGT register with GST) | Yes | To track the GST output tax and filing
6 | Ensure documents are retained in order to justify pricing decisions | 2014-09-05 | 2014-09-05 | - Invoice with 6% GST from supplier | Yes | - To claim input tax for tax supplies in TIC - To claim input tax for PGT expenses | Yes | To keep track and filing invoices and quotation from supplier differently
7 | If necessary, consider getting legal advice in respect of adherence to the Price Control & Anti -Profiteering Act 2011 | 2014-09-05 | 2014-09-05 | - Currently did not engage any legal firm | Yes | - To get legal advice from legal firm/PDC legal department | No | N/A
8 | Communicate price changes to stakeholders, distributors and customers | 2014-09-05 | 2014-09-05 | - Currently no body | Yes | - Staff should be educated and communicate to tourists / customers | No | N/A
9 | Educate & train sales personnel on the new pricing structure | 2014-09-05 | 2014-09-05 | - Currently no body | Yes | - To discuss with deparment head for training | No | N/A

## GST-10
GST Issues Log | [7 empty] | STATUS
[10 empty] | Not yet started | Not Yet Started
|  |  | 10 | Time of Supply |  |  |  |  | In Progress | In Progress | In Progree
[10 empty] | Done | Done
PIC: Michelle
Work Plan |  | Target Date | Completed Date | Info collected / summary of findings | Policy and Procedures (P&P) Changes (Yes /No) | Description of P&P Changes | Tool / System Changes (Yes / No) | Description of Tool / System Changes | Status / Remarks
1 | Establish processes to account for GST at the Basic Tax Point (BTP) | 2014-09-05 | 2014-09-05 | 2 type of sales - Cash and credit term | Yes | To keep track the GST filiing date based on ATP | No | N/A
a | For supplies of all goods and services, the BTP is taken to be : i) Goods sold by PGT - date the goods are " made available" to receipient | 2014-09-05 | 2014-09-05 | - Issuance of receipt for cash sales - Issuance of Invoice for credit term | No | N/A | Yes | Issuance of tax invoice for both
|  |  |  | * Tours - tourist pay in advance to book the tour, we collect money in advance to secure the date and book for tour guide | ?? | Please advise to follow which date BTP or ATP
| ii) Services - date when the service is performed, and | 2014-09-05 | 2014-09-05 | - Received invoice after services performed | Yes | To keep track of the invoice receive, must be within 21 days | Yes | To file for GST input tax return
| iii) Disposal/transfer of business assets (date when goods are transferred/disposed of) | 2014-09-05 | 2014-09-05 | Currently no process | Yes | To date the assets been transferred / disposal | Yes | To issue tax invoice & and account for GST
2 | Establish processes to identify when BTP is overridden by Actual Tax Point (ATP) | 2014-09-05 | 2014-09-05 | Currently no process | Yes | Refer to flow chart (sales, expenses and consignment sales) | Yes | To issue tax invoice and file for GST
3 | Decide on policy whether to take advantage of the 21-day rule from BTP | 2014-09-05 | 2014-09-05 | Cash term - based on ATP (when payment received) Credit term - to use 21 days rule | Yes | To ensure invoice issue within 21 days To ensure invoice from supplier receive in 21 days
a | If yes, establish policy to issue tax invoice within 21 days after BTP (provided payment is not received before the BTP) | 2014-09-05 | 2014-09-05 | To establish policy , issue tax invoice within 21 days for credit terms * Tours - payment receive in advance |  | Please advise to follow which date BTP or ATP
b | Ensure tax invocing is triggered by processed/approved service order within 21 days, and | 2014-09-05 | 2014-09-05 | Currently invoice is issued within 21 days Invoice from supplier may be delay after BTP | Yes | To inform supplier to issue tax invoice within 21 days | No | N/A
c | Identify any instances where you may wish to apply to the DG to be granted an extension of the 21-day rule (monthly or quarterly unit holder/policyholder statements) |  |  | No
4 | Identify instances when advance payments/deposits do not create a tax point Eg. security deposits such as your collateral "bond" receipts which are not treated as a payment received by you. It will also include refundable deposits and deposits forfeited to compensate you for loss or damages |  |  | - Advance payment to supplier - Advance payment received from customers |  | Please advise to follow which date BTP or ATP
5 | Seek clarification, when required, of " date payment received" for various modes of payment: i) Book-entries ii) Cash receipts iii) Direct debit/credit and receipts/standing orders iv) Telegraphic Transfer v) Cheques vi) Payment via internet banking | 2014-09-05 | 2014-09-05 | - book entries based on date payment received and bank in - Payment received advance from tourist for tour booking | No | N/A | No | N/A
6 | Put in place processes and system to monitor the trigger point for time of supply and ensure GST is accounted for appropriately | 2014-09-05 | 2014-09-05 | - A process and system to monitor GST is accounted to be prepared | Yes | A process flow | No | N/A
7 | Review listing of all services provided and identify these that qualify as continuous services | 2014-09-05 | 2014-09-05 | - Selling of merchandise, tours & consignment products (Continuous service) - Payment receive in advance for tour booking (continuous service) | No | N/A | No | N/A
8 | Establish policy and processes to account for GST correctly on contnuous services | 2014-09-05 | 2014-09-05 | - To prepare a process & policy for continous services | Yes | A new policy and process | No | N/A
9 | Communicate policies and processes to relevant staff | 2014-09-05 | 2014-09-05 | - Currently no body | Yes | To discuss with head of department on policies and process | No | N/A
Note 1 : the above must also apply to zero rated and exempt supplies made by you as you are required to account/report these in your GST return
Note 2 : For imported services, the tax point is the date payment is made

## GST-10 Appendix 1
(Sales) Basic Tax Point - PGT/TIC
YES
Goods sold in TIC
Payment received or tax invoice issued before the BTP
YES
Actual Tax Point (ATP) Payment received in Cash & goods are made available to customers/recipient
Tax invoice issued within 21 days after BTP?
NO
Actual Tax Point (ATP) Date of issuance of tax invoice
Basic Tax Point
NO
Basic Tax Point (BTP)

## GST-10 Appendix 2
(Expenses) Basic Tax Point - PGT/TIC
Payment done or tax invoice issued before the BTP
YES
Actual Tax Point (ATP) Payment paid in cash / Paid in advance as deposit upon reciving of tax invoice
Tax invoice received within 21 days of BTP?
NO
Actual Tax Point (ATP) Tax invoice date? or date receive of tax invoice??
Basic Tax Point
Basic Tax Point (BTP)
* Goods received
* Service performed
*Disposal /transfered of Business assets
YES
NO

## GST-10 Appendix 3
(Consignment) Basic Tax Point - PGT/TIC
End of the month closing of sales
Basic Tax Point (BTP)
Consignor supplied goods to TIC ("consignee")
Consignee issue statement of sales to consignor to inform quantity of goods sold
Actual Tax Point
Consignor issue an invoice to TIC on actual number of goods sold
(21 days from the date of receipt of the statement of sales)
After 12 months, the remaining stock had not been sold, the consignor needs to issue a tax invoice within 21 days after the 12 months period has lapsed?

## GST-11
GST Issues Log | [7 empty] | STATUS
[10 empty] | Not yet started | Not Yet Started
|  |  | 11 | Commissions Received |  |  |  |  | In Progress | In Progress | In Progress
[10 empty] | Done | Done
PIC: Michelle/Janice
Work Plan |  | Target Date | Completed Date | Info collected / summary of findings | Policy and Procedures (P&P) Changes (Yes /No) | Description of P&P Changes | Tool / System Changes (Yes / No) | Description of Tool / System Changes | Status / Remarks
1 | Identify the commissions received by PGT | 2014-09-18 | 2014-09-13 | Selling of GTF ticket in year 2012 | No | N/A | No | N/A
2 | Review current contracts on the availability of GST clauses (especially for contracts that will span until GST implementation date). | 2014-09-18 | 2014-09-13 | No contract/agreement was signed between GTF and PGT. No ticket selling in PGT for year 2013-2014 | No | N/A | No | N/A
3 | Evaluate whether current contracts will be required to be revised if it span through GST implementation date. | 2014-09-18 | 2014-09-13 | Nil | No | N/A | No | N/A
4 | Establish process to include GST clause in all new service agreement (where necessary). | 2014-09-18 | 2014-12-01 | Will establish a new process to include GST if PGT provide services on behalf vendor | No | To prepare a process for commision receive in next future | No | N/A
5 | Determine whether PGT will issue tax invoice or the vendor will issue a self-billed invoice to PGT. | 2014-09-18 | 2014-09-13 | Vendor should issue a tax invoice to PGT for commission received | Yes | To follow with vendor if PGT continue to provide the service | No | N/A
6 | Establish process and procedures to account GST on the commissions received in the current taxable period (earlier of payment received or tax invoice issued). | 2014-09-18 | 2014-09-13 | Will establish a new process on time of supply to account for GST if PGT continuously provide services on behalf vendor | Yes | To prepare a process for time of supply in next future | No | N/A
7 | Communicate the GST implications to the vendors and agree on which party to bear the GST cost. | 2014-09-18 | 2014-09-13 | To communicate with vendor in next future | No | N/A | No | N/A
8 | Implement the required changes on the process and procedures. | 2014-09-18 | 2014-09-13 | Nil | No | N/A | No | N/A
9 | Educate employee on the changes. | 2014-09-18 | 2014-09-13 | To communicate with staff about GST impact on commission received | No | N/A | No | N/A

## GST-12
GST Issues Log | [7 empty] | STATUS
[10 empty] | Not yet started | Not Yet Started
|  |  | 12 | Sundry Income & Misc Expenditure |  |  |  |  | In Progress | In Progress | In Progree
[10 empty] | Done | Done
PIC: Michelle
Work Plan |  | Target Date | Completed Date | Info collected / summary of findings | Policy and Procedures (P&P) Changes (Yes /No) | Description of P&P Changes | Tool / System Changes (Yes / No) | Description of Tool / System Changes | Status / Remarks
1 | Identify the type of income and expenses that are posted into sundry receipt and general expense account | 2014-09-11 | 2014-09-09 | As per list attached | Yes | Two type of suppliers - GST register and non GST register | Yes | To mannually keep track suppliers for GST or non GST, and input tax or no input tax incurred. Some of the suppliers are unique as they might be the only supplier for certain goods | Not yet started
2 | Ascertain the GST treatment on each type of income and expense identified | 2014-09-11 | 2014-09-09 | As per list attached | Yes | To imposed 6% of GST for all sales (taxable supply) | Yes | POS System in TIC will be upgraded | POS system to be upgraded in Feb 2015 (According to vendor)
3 | Identify the process and system change required to account for GST appropriately | 2014-09-11 | 2014-09-09 | Currently sales & purchases with no gst impact | Yes | To account 6% input tax and impose 6% output tax for all taxable supply | Yes | POS System in TIC will be upgraded | POS system to be upgraded in Feb 2015 (According to vendor)
4 | Implement the process and system changes | 2014-09-11 | TBA | Currently POS system without GST compliance | Yes | To upgrade POS system | Yes | POS System in TIC will be upgraded | "
5 | Communicate the updated process and system changes to the relevant employees | 2014-09-11 |  | To discuss with head of department | No | N/A | No | N/A

## GST-12 Appendix 1
Penang Global Tourism Sdn Bhd
Sundy Income/Other Income | Tax Coding | GST Impact
|  | Standard Rated | Zero Rated | Exempted | Out-of-Scope
Sales - Souvenirs | SR | x
Sales - Tours (by travel agent/PGT engage a tour guide) | SR | x
Sales - Rapid Passport | SR | x
Sales - Korea Exhibition Art | SR | x
Sales - Stamps | SR | x
Misc Expenditure
Stamp duty and Administrative charge for contract | TX | x
Penalty under estimate Tax | OP |  |  |  | x

## GST-12 Appendix 2
Invoice from Suppliers (consignment goods / purchases)
Payment proess
Matching invoices with merchandise sales record/Official receipts
Invoice verified, checked and signed by Department Head
Return to Supplier/Vendor
YES
NO

## GST17 &18
GST Issues Log | [7 empty] | STATUS
[10 empty] | Not yet started | Not Yet Started
|  |  | 17 & 18 | Blocked Input Tax & Entertainment Expenditure |  |  |  |  | Not yet started | In Progress | In Progree
[10 empty] | Done | Done
PIC: Michelle
Work Plan |  | Target Date | Completed Date | Info collected / summary of findings | Policy and Procedures (P&P) Changes (Yes /No) | Description of P&P Changes | Tool / System Changes (Yes / No) | Description of Tool / System Changes | Status / Remarks
GST 17
1 | Identify all potential blocked input tax expenditure items that PGT will incur. | 2014-09-11 | 2014-09-11 | As per listing | No | N/A | Yes | To capture the transaction under Block Input Tax coding
2 | Assess the GST financial impact on PGT’s bottom line and whether any changes in policies required | 2014-09-11 | 2014-09-11 | Additional cost 6% incurred to PGT | No | N/A | Yes | To capture the transaction under Block Input Tax coding
3 | Review current accounting and recording of these blocked input tax expenditures and apply the appropriate tax codes so that no input tax credit is claimed in respect of these expenses. | 2014-09-11 | 2014-09-11 | Currently recorded under Chart Of Account (Tax Coding) | No | N/A | Yes | To change the UBS coding base on transaction approach
GST 18
1 | Identify expenditures which would falls to be regarded as "entertainment expense" for GST purposes. | 2014-09-11 | 2014-09-11 | - Training - Team Building - Annual Dinner - Dinner with BOD director | No | N/A | Yes | Transaction under standard rated (TX) , Input tax credit is allow
2 | Categories the various entertainment expenses into the following:- - own employees; - existing customers; - mix of employees/customers and others; - all others | 2014-09-11 | 2014-09-11 | Most of the entertainment were spent for travel agents, media, guests. | No | N/A | Yes | To capture the transaction under Block Input Tax code
3 | Establish controls and procedures to ensure that entertainment expenses incurred or claimed are correctly categorised with input tax incurred segregated between blocked and claimable amount. | 2014-09-11 |  | Analyse each of every entertainment claims/billing | Yes | A procedure for entertainment checking will be prepared | Yes | To create 2 ledger for entertainment - Entertainment fee (Blocked Input tax) - Entertainment fee (Input Tax Claimable)
4 | Establish process and procedures to review and verify the status of employees and existing customers for which input tax incurred on entertainment expenses is claimed. | 2014-09-11 |  | No GST input tax is allowed for entertainment expeses to travel agent, media fam, guests | No | No existing customer. A procedure for entertainment checking will be prepared | Yes | To create 2 ledger for entertainment - Entertainment fee (Blocked Input tax) - Entertainment fee (Input Tax Claimable)
5 | Establish process and procedures to ensure that invoices and documentation relating to input tax claim on entertainment expenses are complete, correct and in order. Full or simplified tax invoice, name of company, name of persons entertained and other key details need to be maintain and kept to support the input tax claimed | 2014-09-11 | 2014-09-11 | Currently no tax invoice, invoice will be matching with PO,PR/Memos | Yes | Work flow of invoice checking to be prepared | No | N/A
6 | Review current procedures and processes for accounting for entertainment expenses and determine the changes in procedures, processes and systems required to cater for the new GST impact and its implications. | 2014-09-11 |  | PGT entertainment expenses for travel agents, media and etc. Entertainment expenses for staff are annual dinner, food and refreshment | Yes | To separate the entertainment billing for employees and other person To prepare a process on entertainment billing checking | Yes | To create 2 ledger for entertainment - Entertainment fee (Blocked Input tax) - Entertainment fee (Input Tax Claimable)
7 | Consider if general ledger accounts need to be split and new accounts established. Proper tax coding should be assigned to each account, if account coding method is adopted. | 2014-09-11 |  | Currently GL account on project basis | Yes | To discuss with consultant/pdc accountant on how to split the ledger based on tax code | Yes | To configure the GL account code and matching with the tax coding
8 | Implement procedures, processes and systems changes required to support a proper claim of input tax incurred on entertainment expenses. | 2014-09-11 |  | Currently no practice | Yes | Prepare a work flow on entertainment billing checking | Yes | To create 2 ledger for entertainment - Entertainment fee (Blocked Input tax) - Entertainment fee (Input Tax Claimable)
9 | Educate employees on the procedures, processes and systems changes. | 2014-09-11 |  | To communicate with staffs on entertainment expenses claims | No | N/A | No | N/A

## GST17 &18 Appendix
GST 17 -Blocked Input Tax
Blocked input tax credit items
No. | (1) General ledger account code (blocked input tax) Please provide the GL code number | (2) General ledger account description Please provide a brief description of expense(s) | Further description | (3) GST tax code (expense) Please select from drop down menu | Drop-down menu data
Column (3)
| 9006/000 | Medical Fee | Medical Fee | - Medical expenses | - Club subscription fees
| 9006/001 | Medical Fee | Medical Fee | - Medical expenses | - Medical & personal accident insurance premium or takaful
| 9008/000 | Insurance | Insurance | - Medical & personal accident insurance premium or takaful | - Medical expenses
|  | - Hospitalize/Group Term Life/Travel Insurance | - Hospitalize/Group Term Life/Travel Insurance | - Medical & personal accident insurance premium or takaful | - Family benefits
| 9109/000 | - Food & Refreshment (for guest) | - Food & Refreshment (for guest) | - Entertainment expenses (other than employees or existing customers) | - Entertainment expenses (other than employees or existing customers)
| 9221/001 | Tactical Campaign - Taiwan | - Transportation (Hiring of passenger car/van) | - Supply, importation or hire of passenger motor car | - Supply, importation or hire of passenger motor car
| 9300/004 | Familiazation Trip | - Entertainment for Travel Agent, Media and etc | - Entertainment expenses (other than employees or existing customers)
| 9300/004 | Familiazation Trip | - Transportation (Hiring of passenger car/van) | - Supply, importation or hire of passenger motor car
| 9300/006 | Lunch/Dinner Hosting | - Entertainment for guests/Travel agent | - Entertainment expenses (other than employees or existing customers)
| 9300/031 | PGT Networking with Tourism Player | - Entertainment for tourism player/board of directors | - Entertainment expenses (other than employees or existing customers)
| 9300/032 | Incentive for MICE | - Entertainment for MICE Group | - Entertainment expenses (other than employees or existing customers)
| 9300/032 | Incentive for MICE | - Transportation (Hiring of passenger car/van) | - Supply, importation or hire of passenger motor car
| 9300/040 | George Town Literary Festival | - Transportation (Hiring of passenger car/van) | - Supply, importation or hire of passenger motor car
| 9300/046 | The Spring Festorama | - Food & Refreshment for guest | - Entertainment expenses (other than employees or existing customers)
| 9300/046 | The Spring Festorama | - Transportation (Hiring of passenger car/van) | - Supply, importation or hire of passenger motor car

## GST-19
GST Issues Log | [7 empty] | STATUS
[10 empty] | Not yet started | Not Yet Started
|  |  | 19 | Employee Benefits |  |  |  |  | In Progress | In Progress | In Progress
[10 empty] | Done | Done
PIC: Michelle & Hooi Leng
Work Plan |  | Target Date | Completed Date | Info collected / summary of findings | Policy and Procedures (P&P) Changes (Yes /No) | Description of P&P Changes | Tool / System Changes (Yes / No) | Description of Tool / System Changes | Status / Remarks
1 | Identify and determine the category of goods or services that are provided to employees. | 2014-09-11 | 2014-09-11 | Nil | No
2 | Identify items covered under your employee benefits and its respective GST treatment | 2014-09-11 | 2014-09-11 | Refer to Appendix I | Yes | Management is to decide and come out with a new P&P | No | N/A
3 | Identify items that are subjected to deemed output tax | 2014-09-11 |  | Uniform to driver No free goods to employees | No | N/A | Yes | To create a GL code - employee benefits (DS)
4 | Seek clarification from Customs on any ambiguity in GST treatment | 2014-09-11 |  | Nil
5 | Update HR policy, guidelines, processes and systems changes for GST compliance on free goods to employees | 2014-09-11 | 2014-09-11 | Nill. No free goods to employees | No | N/A | No | N/A
6 | Develop a process to ensure that deemed output tax is correctly accounted in PGT’s GST returns based on time of supply | 2014-09-11 | 2014-09-11 | Based on Actual Tax Point - Tax Invoice receive | Yes | A process to account for output tax based on time of supply is prepared | Yes | To generate invoice and account output tax
7 | Educate staff on the updated policy, processes and systems changes | 2014-09-11 | 2015-01-31 | To communicate with staff once new policy is done

## GST-19 Appendix
Appendix I
Employee Benefits |  | Type | GST Tax Code
i | Medical
| - Medical Claim | Claims | BL
ii | Insurance
| - Group Hospital & Surgical | non-cash | BL
| - Group Term Life | non-cash | BL
iii | Allowance
| - Guaranteed Minimum Overtime Allowance | Cash | OP
| - Handphone Allowance | Cash | OP
| - Outstation Meal Allowance | Cash | OP
| - Airport Meal Allowance | Cash | OP
iv | Claim
| - Overtime | Cash | OP
| - Mileage | Cash | OP
| - Parking & Toll | Claims | TX
| - Handphone (as per bill) | Claims | OP
v | Airport Car Park | Claims | TX
vi | Rapid Bus Monthly Pass | Claims | OP
vii | Uniform | Claims | DS
viii | Gratuity | Cash | OP
ix | Training & Development
| - Workshop/Course | non-cash | TX
| - Teambuilding | non-cash | TX
x | Company Car | non-cash | OP
xi | Annual Dinner | non-cash | TX

## GST-19 Appendix 2
Deemed Supplies - Time of Supply
Actual Tax Point
Goods purchase
(tax invoice/simplified tax invoice)
Account for GST Output tax
Input Tax Credit

## GST-20
GST Issues Log | [7 empty] | STATUS
[10 empty] | Not yet started | Not Yet Started
|  |  | 20 | Reimbursement of Staff Expenses / Claims |  |  |  |  | In Progress | In Progress | In Progree
[10 empty] | Done | Done
PIC: Michelle
Work Plan |  | Target Date | Completed Date | Info collected / summary of findings | Policy and Procedures (P&P) Changes (Yes /No) | Description of P&P Changes | Tool / System Changes (Yes / No) | Description of Tool / System Changes | Status / Remarks
1 | Identify all types of reimbursement claims made by staff of PGT. | 2014-09-11 | 2014-09-11 | Refer listing | No | N/A | No | N/A
2 | Categorise reimbursement claims as business expenses or private expenses. | 2014-09-11 | 2014-09-11 | Yes. All reimbursement claims are business expense | No | N/A | No | N/A
3 | Review and establish systems and processes to deal with reimbursement claims to ensure that input tax claims are maximised and that blocked input tax is not claimed | 2014-09-11 |  | Claims form/Statement of claims is use for reimburesment | Yes | To analyse each of every claims whether fall under input tax claim or block input tax | No | N/A
4 | Establish a standard policy on employees reimbursement (e.g. fringe benefits, business expenses, etc.) taking into the consideration the following requirements:
| Valid tax invoice to be provided by employee (tax invoice must be in the name of the relevant entity claiming the input tax) | 2014-09-11 |  | All tax invocie /simplified tax invoice has to be the name of PGTSB | Yes | To prepare a process work flow for reimbursement | No | N/A
| GST is genuine (i.e. issued by GST registered supplier) | 2014-09-11 |  | Suppliers must be register with GST | Yes | To update and checking the suppliers master listing from time to time | No | N/A
| Where no valid tax invoice provided (i.e. PGT cannot claim input tax), to consider whether PGT to absorb cost of GST not claimable, or, to disallow reimbursement of GST element to the employee. | 2014-09-11 |  | No valid tax invoice provided (Air fare, Hotel Accommodation, sundry income, food and refreshment) | Yes | Management to decide whether to absorb the 6% of GST not claimable or disallow reimbursement of GST by employees | No | N/A
8 | No input tax is claimed by PGT where it is disallowed. For example: - No valid tax invoice available - Expenses relate to blocked input tax items - Expenses where foreign GST/VAT is incurred (foreign GST/VAT cannot be claimed under Malaysian GST system) | 2014-09-11 |  | Input tax disallow : - foreign GST/VAT (Hotel/Transportation) - Block input tax (Entertainment for other person) | Yes | To check claim reimbursement based on ITC guideline | No | N/A
9 | Establish processes, documentation and system changes required to implement policy. | 2014-09-11 |  | A procedure of reimbursement ill be prepared | Yes | To prepare a procedure of reimbursement by staff | Yes | To capture transaction base on GST tax coding
10 | Ensure record keeping requirements are adequate for GST purposes | 2014-09-11 |  | All reimbursement must have supporting document (tax invoices, receipts) | Yes | To include in the procedure | No | N/A
11 | Update current processes and systems to reflect the GST treatment. | 2014-09-11 |  | Refer to flow chart | Yes | To check reimbursment base on GST guideline : - Valid Tax Invoice - Input tax Claimable - Blocked input tax | No | N/A
12 | Educate staff on processes and systems changes. | 2014-09-11 |  | To update and communicate to staff once the procedure ready

## GST20 - Appendix 1
GST 20– Reimbursement of staff expenses / claims
No. | (1) Reimbursement of expense Please provide a brief description |  | (2) General Ledger account code Please provide GL account code number | (3) Is reimbursement in respect of business expense? Please select from drop down menu | (4) Is reimbursement made to a non-employee? Please select from drop down menu | (5) GST tax code (expense) Please select from drop down menu | Drop-down menu data
[7 empty] | Column (3) | Column (4) | Column (5)
1 | Medical Fee | Medical Fee | 9006/000 | No | No | BI | Yes | Yes | FITC
2 | Medical Fee | Medical Fee | 9006/001 | No | No | BI | No | No | NITC
3 | Allowance | H/P Allowance, Food Allowance | 9002/000 | No | Yes |  |  |  | BI
4 | Mileage/Toll Claims/Petrol | Mileage/Toll Claims/Petrol | 9014/000 | Yes | No
|  | - Petrol Refill |  | Yes | No
|  | - Mileage Reimbursement |  | Yes | No
|  | - Parking Fees Reimbursement |  | Yes | No
5 | Tic-Mileage/Toll Claims/Petrol | Tic-Mileage/Toll Claims/Petrol | 9014/001 | Yes | No
|  | - Mileage Reimbursement |  | Yes | No
|  | - Parking Fees Reimbursement |  | Yes | No
|  | - Rapid Passport Monthly |  | Yes | No
6 | Local Travel | - Hotel Accommodation | 9015/000 | Yes | No
|  | - Air Fare (Domestic) | 9015/000 | Yes | No
|  | - Transportation (Eg Taxi, Mrt) | 9015/000 | Yes | No
|  | - Parking Fees | 9015/000 | Yes | No
|  | - Food And Beverages Reimbursement | 9015/000 | Yes | No
7 | Staff Uniform | Staff Uniform (Not Stated In Contract) | 9017/000 | No | No
8 | Telephone/Emails/Fax | - Telephone Charges | 9101/000 | Yes | No
|  | - H/P Rreimbursement From Staffs (Monthly Rm50/According To Billing) | 9101/000 | Yes | No
|  | - H/P Data Usage | 9101/000 | Yes | No
9 | Postage & Courier | Postage & Courier | 9102/000 | Yes | No
10 | Stationery & Supplies | Stationery & Supplies | 9105/000 | Yes | No
11 | Refreshment & Food | - Food & Refreshment For Staff | 9109/000 | No | Yes
|  | - Refreshment For Bod/Meeting | 9110/000 | Yes | No
12 | Upkeep of M/Vehicle | - Insurance/Road Tax | 9111/000 | Yes | No
13 | Familiazation Trip | - Tour Guide/Trishaw/Nature Tour | 9300/004 | Yes | Yes | BI
|  | - Entertainment For Travel Agent (Lunch, Dinner) | 9300/004 | Yes | Yes | BI
|  | - Souvenirs For Delegates | 9300/004 | Yes | No
14 | Hosting of events | - Social Media Ads | 9300/024 | Yes | No
|  | - Allowance For Rela Volunteers | 9300/024 | Yes | No
15 | Tourism Promotion | - Hotel Accommodation (overseas) | 9400/108 - 9400/118 | Yes | No
|  | - Transportation (Overseas) |  | Yes | No
|  | - Meal Allowance |  | Yes | No
|  | - Souvenirs |  | Yes | No
|  | - Internet Charges |  | Yes | No
|  | - Food & Refreshment |  | Yes | No
|  | - Wrapping Cost |  | Yes | No
|  | - Visa |  | Yes | No
No

## GST-20 Appendix 2
Finance Dept to review of claim and checking (receipts,billing)
Department head to counter check and verify
YES
Approved by CEO/MD/GM
NO
Reimbursement form fill in by employee
Return to employee
YES
Payment process
NO

## GST-20 Appendix 3
Finance Dept to review of claim and checking
Department head to counter check and verify
YES
Approved by CEO/MD/GM
NO
Reimbursement form fill in by employee
Return to employee - To get a new tax invoice
- PGT to absorb the 6% or Employees are not allow to claim the 6% GST incurred
YES
Payment process
NO
GST Impact - To review
- Valid Tax Invoice (Bill to PGTSB) - Input Tax Claimable - Blocked input tax
NO

## GST-21
GST Issues Log | [7 empty] | STATUS
[10 empty] | Not yet started | Not Yet Started
|  |  | 21 | Goods Provided for Free |  |  |  |  | In Progress | In Progress | In Progress
[10 empty] | Done | Done
PIC:
Work Plan |  | Target Date | Completed Date | Info collected / summary of findings | Policy and Procedures (P&P) Changes (Yes /No) | Description of P&P Changes | Tool / System Changes (Yes / No) | Description of Tool / System Changes | Status / Remarks
1 | Review and assess marketing strategies from different channels to determine whether any cash / cash rebate, free goods, free services, vouchers, or any other kind of incentives provided. | 2014-09-11 |  | Only free goods/souvenirs give out : Type of souvenirs/gifts: - Memo pad - Pen - Mugs - Pewter trishaw - Tiles Fridge Magnet - Cotton Bags - Paper bag - Collar Pin - Books - Tau Sar Pneah - ?? Food or souvenirs - Tourism Booklet - ??? - Tourism DVD - ??? | No | N/A | No | N/A
2 | Segregate and record free gifts given from own stock and those received from suppliers. | 2014-09-11 |  | Currently record inventory based on product basis only | Yes | To have addiditonal spreadsheet on company/association that request for free goods | Yes | To account for GST if the free gifts exceeded RM500 for each person/company
3 | Analyse feasibility to track GST gift rule (i.e. RM500 per person per year), taking into account amongst others the following: a. Type of goods given for free (e.g. free goods, free services, non-cash voucher, etc.) b. Value of goods given for free c. Frequency of goods given for free d. Ability to identify recipient of free goods (e.g. to employees, distributors, suppliers, etc.) | 2014-09-11 |  | To amend inventory record tracking | Yes | - To include value of the goods inventory record, identify recipient, frequency of free goods given (including, Free souvenirs for Road Show - Overseas, free goods to university/associations/company/person(fam trip/guests)/staffs | Yes | To account for GST (DS) if the free gifts exceeded RM500 for each person/company (Time of supply for free goods given during roadshow : - Date the goods given out during trade show, officer need to record the recipient everyday
4 | Awareness of deemed supplies and GST output tax when formulating marketing strategies in the future. | 2014-09-11 |  | Free goods given for free to support tourism industry players, promote penang during road show | Yes | To discuss with marketing department on the strategies | No | N/A
5 | Management to make strategic decision on whether goods will continue to be given free, the value of such gifts and whether PGT will attempt to track free goods. | 2014-09-11 |  | Free goods given for free to support tourism industry players, promote penang during road show | Yes | To discus with GM & head of department whether goods will be given free in future | No | N/A
6 | Consider alternative marketing structure / packages taking into account the GST implication. | 2014-09-11 |  | To discuss with GM and department head | Yes | To discuss with marketing department on the strategies | No | N/A
7 | Consider proper controls for goods given out for free – map process flow of goods given away free to ensure GST output tax is captured timely. | 2014-09-11 | 2014-12-01 | A process/procedure of free goods requsition and given out will be prepared | Yes | All requsition and free goods given will be followed the process/procedure | No | N/A | To be completed
8 | Determine changes required to existing policy, processes and system to ensure GST output tax is accounted for appropriately for the various incentives / gifts provided. | 2014-09-11 |  | Inventory record for free goods | Yes | To include value, recipient and date goods give out Person-in charge to monitor the goods given out whether is exceed RM500, to be notify Finance Department | No | N/A
9 | Implement changes. | 2014-09-11 | 2014-12-01 | Changes will be implemented once the procedure is done | No | N/A | No | N/A
10 | Educate and communicate policy to staff on policy on free goods. | 2014-09-11 | 2014-11-01 | To communicate with staffs on the policy | No | N/A | No | N/A

## GST-22
GST Issues Log | [7 empty] | STATUS
[10 empty] | Not yet started | Not Yet Started
|  |  | 22 | Free Services |  |  |  |  | In Progress | In Progress | In Progress
[10 empty] | Done | Done
PIC: Michelle/Jason/Darren
Work Plan |  | Target Date | Completed Date | Info collected / summary of findings | Policy and Procedures (P&P) Changes (Yes /No) | Description of P&P Changes | Tool / System Changes (Yes / No) | Description of Tool / System Changes | Status / Remarks
1 | Identify free services provided by PGT and segregate these by its intended recipient (i.e. employees, third party or 'connected persons'). | 2014-09-11 | 2014-09-11 | Free services provided by PGT : 1. Free Cemetery Tour (open to public) 2. Free Guided walk at Botanic Garden (open to public) 3. Free Performance (open to public/travel associate) Question : if we give free services to a company, in return they will put PGT logo in their brochure as suppoted by PGT. Is this consider free services or sponsorship? | No | N/A | No | N/A
2 | Assess the GST treatment and impact for each transaction. | 2014-09-11 | 2014-09-11 | Free tours & performances | Yes | There will be a standard rate charge on each transaction, but no input tax are allow for Tours (entertainment), tax coding will be BL Question : Free performances is consider as entertainment? | Yes | To capture the transaction based on tax coding BL/TX
3 | For each transaction which has a GST impact ensure that the valuation of the supply adheres to the open market value ("OMV"). | 2014-09-11 |  | Two type of senario: 1. Free services provided to public/travel associate (one way supply - no GST impact) 2. Free services provided to company/travel associate in returns with free goods and ads (refer to sponsorship) | Yes | To determine free services and discuss with management / head of deparment on free services strategies ("only services provided for no consideration") | No | N/A
4 | Update processes and systems to track these transactions (services provided for no consideration) and account for GST accordingly. | 2014-09-11 |  | A new process/procedures to be prepared | Yes | Record tracking to be include: - free services to third party with no returns (gst impact = allow to claim input tax) - free services(tours/performances) to third party with no returns (gst impact = input tax blocked) | No | N/A
5 | Educate staff on the updated processes and systems changes | 2014-09-11 |  | To communicate with staff once the process and procedure is ready

## GST-26
GST Issues Log | [8 empty] | STATUS
[11 empty] | Not yet started | Not Yet Started
|  |  | 26 | Sponsorship | [5 empty] | In Progress | In Progress | In Progress
[11 empty] | Done | Done
PIC: All Staff
Work Plan |  | Target Date | Completed Date | Info collected / summary of findings | In - returns | Policy and Procedures (P&P) Changes (Yes /No) | Description of P&P Changes | Tool / System Changes (Yes / No) | Description of Tool / System Changes | Status / Remarks
1 | Identify and categorise sponsorships that PGT has been involved. | 2014-09-18 | 2014-09-17 | Sponsorship given by PGT : a) Publicity (Printing of brochures, billboard, bus wrap) for events (not organize by PGT) b) Performance (Traditional, culture dance) for dinner/events c) Cash Sponsorship d) Dinner/tours/hotel for media & travel agent e) Promoting events in PGT website/Facebook Q : Some sponsorship may not pay directly to organizer, we pay directly to supplier/vendor engaged by PGT, Is this still consider as sponsorship or free services (GST impact)?? | a) by mention PGT and putting PGT logo in their media release b) putting logo in their brochures (supported by PGT) c) putting logo in their brochures (supported by PGT) d) Article/write-up about Penang in their magazine/blogs etc e) putting logo in their brochures (supported by PGT)
2 | Develop a policy on sponsorship/donation arrangement for PGT, taking into the account the following: Sponsorship/Donation received by PGT a) Identify nature of sponsorship/donation received: o Cash; or o Goods; or o Services; or o A hybrid of the above. | 2014-09-18 | 2014-10-15 | A policy on sponsorship/donation need to be prepared (define what are the impact for sponsorship in cash, goods, services) |  | Yes | To prepare a new policy on sponsorship and dontation | No | N/A
| b) Establish process to determine whether PGT shall need to issue tax invoice to the sponsor / donor based on:- i. Any benefits provided by PGT to the sponsor / donor (e.g. advertising, free table during functions, etc) – to issue tax invoice to the sponsor / donor; or ii. No benefit provided by PGT (pure donation) – no issuance of tax invoice required. | 2014-09-18 | 2014-09-17 | Refer to the spreadsheet for sponsorship provide & received by PGT |  | Yes | Prepare a process/procedure to determin the tax invoice involvement | No | N/A
| c) If the issue of a tax invoice is required, establish a process to determine the value of the sponsorship / donation and the amount of GST to be accounted in the tax invoice. | 2014-09-18 |  | To determine the open market value of the sponsorship received/provided |  | Yes | To discuss with department head on the open market value | No | N/A
| d) Establish processes to ensure that GST output tax is properly captured and accounted in the GST return Form GST-03 in the correct taxable period. | 2014-09-18 |  | To prepare a process of capture output tax for sponsorship of goods, amd services |  | Yes | To discuss with PwC
| Sponsorship / Donation made by PGT a) Identify nature of sponsorship/donation given: o Cash; or o Goods; or o Services; or o A hybrid of the above. | 2014-09-18 |  | Sponsorship received by PGT : a) Sponsorship of air tickets for guests b) Cash Sponsorship for events | a & b) by mention sponsor's name and logo in media release, publicity |  |  | No | N/A
| b) Establish process to determine whether PGT shall need to issue tax invoice / received tax invoice as follows:- | 2014-09-18 |  | Refer to the spreadsheet for sponsorship provide & received by PGT |  | Yes | Prepare a process/procedure to determin the tax invoice involvement | No | N/A
| c) If the issue of tax invoice is required, establish process to determine the value of the sponsorship / donation subjected to GST and the amount of GST to be accounted in the tax invoice. | 2014-09-18 |  | To determine the open market value of the sponsorship /received provided |  | Yes | To discuss with department head on the open market value e.g Services / promotion of event in website/facebook | No | N/A
| d) If there is input tax is claimable, establish process to ensure tax invoice are received for input tax claim purposes. | 2014-09-18 | 2014-10-15 | A process for GST output tax and input tax to be prepare |  | Yes | To prepare a process/procedure of input tax for sponsorship given | No | N/A
| e) Establish processes to ensure that GST output and input tax are properly captured and accounted in the GST return Form GST-03 in the correct taxable period. | 2014-09-18 | 2014-10-15 | A process for GST output tax and input tax to be prepare |  | Yes | To prepare a process/procedure to account for output tax | No | N/A
3 | Establish process and policy to ensure that all future contracts or arrangements related to sponsorship / donation arrangement have GST clauses (inclusive / exclusive). | 2014-09-18 | 2014-10-15 | To set a policy for sponsorship provided/received |  | Yes | To set a policy to ensure all gst clauses are include in sponsorship | No | N/A
4 | Determine and implement the processes and systems changes required to incorporate the GST impact and implications related to sponsorship / donation received / made. | 2014-09-18 | 2014-10-15 | Process and system changes to be implemented when the policy & procedure is ready |  | Yes | To implement the system and process based on GST guidelines | No | N/A
5 | Review current accounting and recording of sponsorship / donation (received / made) and determine the appropriate tax codes to be applied. | 2014-09-18 |  | Refer to tax coding |  | Yes | To analyse current accounting (sponsorship provided/received) | Yes | Refer to tax coding
6 | Educate employees on the processes, policies and systems changes. | 2014-09-18 |  | To brief and educate staff when the new policies is ready |  | No | N/A

## GST-26 Appendix 1
Sponsorship provided by PGT :
- Publicity
- Performance
- Cash
- Goods
- Hotel/Dinner/Tour
Benefit in returns :
- Logo
- Booth/ Goods
- by mention PGT in their media release
Tax Invoice to be issued by recipient :
- based on the value of the goods received
No tax invoice involve
Entitle to claim the input tax
(Except for Hotel/Tours/Dinner)
*Block Input Tax
NO
YES

## GST-26 Appendix 2
Sponsorship received :
- Publicity
- Cash
- Hotel/Dinner/Tour
Benefit given :
- Putting donor's logo / name in our media release/publicity
Tax Invoice to be issue by PGT:
- based on the value of the goods received
- inclusive of GST
No tax invoice involve
NO
YES

## GST-27
GST Issues Log | [7 empty] | STATUS
[10 empty] | Not yet started | Not Yet Started
|  |  | 27 | Payment to Federal & State Governments, Statutory Bodies and Local Authorities |  |  |  |  | In Progress | In Progress | In Progress
[10 empty] | Done | Done
PIC: Michelle
Work Plan |  | Target Date | Completed Date | Info collected / summary of findings | Policy and Procedures (P&P) Changes (Yes /No) | Description of P&P Changes | Tool / System Changes (Yes / No) | Description of Tool / System Changes | Status / Remarks
1 | Identify and list all payments made to local authorities and statutory bodies. | 2014-09-18 | 2014-09-13 | Payment made to local authorities & statutory bodies : - Company Car Road Tax - License fees for Tourist Information Centre (TIC) - PTPTN loan repayment in respect of staff's salary - EPF, SOCSO, PCB in respect of staff's salary - Adsvetising permit in TIC - Deposit to MPPP for banners | No | N/A | No | N/A
2 | Review and confirm prior to GST implementation whether GST would apply on the relevant payment. | 2014-09-18 | 2014-09-13 | No GST impact on these payment (out of scope) | No | N/A | No | N/A
3 | Implement and determine the processes and system changes to track and confirm whether GST applies on a payment to local authorities and statutory bodies prior to making payment. | 2014-09-18 | 2014-09-13 | Nil - All payment to local authorities & statutory bodies are under R&E (Regulations & Enforcement) | No | N/A | No | N/A
4 | Establish a process to ensure PGT do not claim input tax on payments to federal & state governments. | 2014-09-18 | 2014-09-13 | A process/procedure of input tax credit claimable to be prepared | Yes | To check with PwC consutant on what are the payment to local statutory bodies is allow for input tax claim | No | N/A
5 | Implement processes and systems changes. | 2014-09-18 | 2014-09-13 | Nil | No | N/A | No | N/A
6 | Educate staff on the processes and systems changes. | 2014-09-18 | 2014-09-13 | Nil | No | N/A | No | N/A