## GST Checklist-PDCPH
PDC PREMIER HOLDINGS SDN BHD GST WORK PLAN CHECKLIST | [8 empty] | Not yet started
In Progress
Done
Project Lead: Puan Vasandi Subramaniam
Category | List of Issues Log |  | PIC | Targeted Month | Target Date | Completed Date | Status | Remarks
A | GST 01 | Strategic: Budgeting and Resource Requirement for GST Implementation | Puan Vasandi Subramaniam | August |  |  | Not yet started
A | GST 03 | Strategic: Preferred vendor management | Puan Indah |  |  |  | Not yet started
A | GST 04 | Strategic : Price Rebalancing | Puan Sangeetha |  |  |  | Not yet started
A | GST 28 | Transitional: Inclusion of GST clause in all contracts | Puan Vasandi/Puan Juliana |  |  |  | Not yet started
B | GST 09 | Compliance: Time of Supply | Puan Sangeetha/Puan Juliana | September and October |  |  | Not yet started
B | GST 10 | Compliance: Sundry income and Miscellaneous Expenditure | Puan Sangeetha |  |  |  | Not yet started
B | GST 15 | Compliance: Blocked Input Tax | Puan Sangeetha/Puan Juliana |  |  |  | Not yet started
B | GST 16 | Compliance: Entertainment expenditure | Puan Sangeetha |  |  |  | Done
B | GST 17 | Compliance: Employee Benefits | Puan Vasandi/Puan Sangeetha |  |  |  | In Progress
B | GST 18 | Compliance: Reimbursement of staff expenses/claims | Puan Vasandi/Puan Sangeetha |  |  |  | Not yet started
B | GST 19 | Compliance: Goods provided for free | Puan Vasandi/Puan Sangeetha |  |  |  | Not yet started
B | GST 23 | Compliance: Disposal of fixed assets | Puan Indah/Puan Sangeetha |  |  |  | Not yet started
B | GST 24 | Compliance: Sponsorship | Puan Vasandi/Puan Sangeetha |  |  |  | Not yet started
B | GST 25 | Compliance: Payments to Federal & State Governments, Statutory Bodies and Local Authorities | Cik Swaran/Puan Sangeetha |  |  |  | Not yet started
C | GST 11 | Compliance: De Minimis and Incidental Financial Supplies | Puan Sangeetha | September and October |  |  | Not yet started
C | GST 12 | Compliance: Apportionment of 'Indirect Costs' for Recovery of Input Tax | Puan Sangeetha |  |  |  | Not yet started
C | GST 21 | Compliance: Inter-company Supplies and Cross Charges to Related Entities | Puan Sangeetha/Puan Juliana |  |  |  | Not yet started
C | GST 22 | Compliance: Open Market Value ("OMV") | Puan Sangeetha/Puan Juliana |  |  |  | Not yet started
D | GST 05 | Compliance: Tax coding for GST | Puan Sangeetha/Puan Juliana | September and October |  |  | Not yet started
D | GST 07 | Compliance: Issuance of Tax Invoices | Puan Sangeetha |  |  |  | Not yet started
D | GST 08 | Compliance: GST Adjustments to Tax Invoices with Credit and Debit Notes | Puan Sangeetha |  |  |  | Not yet started
D | GST 14 | Compliance: Accounting recognition vs GST recognition for input tax claim | Puan Sangeetha/Puan Juliana |  |  |  | Not yet started
E | GST 06 | Compliance: Record keeping requirements for GST purposes | Puan Sangeetha/Puan Juliana | November |  |  | Not yet started
E | GST 13 | Compliance: Documentation to Claim Input Tax Credit | Puan Sangeetha |  |  |  | Not yet started
E | GST 20 | Compliance: Reimbursement vs disbursement | Puan Vasandi/Puan Sangeetha |  |  |  | Not yet started
E | GST 26 | Compliance: GST Relief for Bad Debts | Puan Sangeetha/Puan Juliana |  |  |  | Not yet started
F | GST 02 | Strategic: CAPEX | Puan Sangeetha | December to March |  |  | Not yet started
F | GST 27 | Transitional: Cancellation of Your Service Tax License | Puan Vasandi |  |  |  | Not yet started
F | GST 29 | Transitional : Contracts spanning GST start date | Puan Sangeetha/Puan Juliana/ Puan Vasandi |  |  |  | Not yet started

## Readiness report
GST Issues Log | [7 empty] | STATUS
[10 empty] | Not yet started | Not Yet Started
|  |  | 04 | Preferred Vendor Management |  |  |  |  | Not yet started | In Progress | In Progree
[10 empty] | Done | Done
PIC: Michelle
Work Plan |  | Target Date | Completed Date | Info collected / summary of findings | Policy and Procedures (P&P) Changes (Yes /No) | Description of P&P Changes | Tool / System Changes (Yes / No) | Description of Tool / System Changes | Status / Remarks
1 | Analyse existing supplies/vendors if they are potiental gst registrant | 2014-09-05 | 2014-09-05 | Prepare a vendor listing and analyse | Yes | To decide if want to continue with non register vendors | Yes | To mannually keep track vendor for GST or non GST
2 | Determine if management would establish policy on preferred vendor program or continue engaging non register vendors | 2014-09-05 | 2014-09-05 | Most of the suppliers/vendor are potential gst registrant Some of the are uncertain | Yes | To decide if want to continue with register or non register vendor (subject to PGT's future outcome on whether to register with gst) | Yes | To mannually keep track vendor for GST or non GST
3 | If management decides to implement the programme, communication policy to vendors and develop procedures to track GST status of vendors | 2014-09-05 | 2014-09-05 | To follow up & keep track with supplies/vendors who are potential gst registrant and collect gst documentation from them | Yes | To filing related GST documentation provided by suppliers | No | N/A
4 | If management decides to continue with the current practices and engage non-registered vendors, ensure the GST status of the vendor and the transaction are tracked seperately | 2014-09-05 | 2014-09-05 | Management to decide whether to continue with non register supplier. PGT will have to engage with non register supplier if the supplies are unique. | No | N/A | No | N/A
5 | Update the changes to processes and systems to enable tracking of vendors and their transactions | 2014-09-05 | 2014-09-05 | To decide on the tax coding exercise, base on account or transaction approach | Yes | To analyse the each of every expenses base on tax coding approach | Yes | UBS account code might be affected
6 | Educate staff on the updated processes and system changes | 2014-09-05 | 2014-09-05 | Currently no body | Yes | Additional task for accounts executive | No | N/A
7 | Communicate with procurement/vendors on PGT's policy on preferred vendor scheme | 2014-09-05 | 2014-09-05 | Currently no body | Yes | All staffs to involve | No | N/A

## GST04 - Vendor management
GST 04 - Preferred Vendor Management
No. | (1) Name of vendors & suppliers Please provide the name of vendors & suppliers of PGT | (2) Is the vendors/suppliers is/will be GST registrant? Please select from drop down menu | (3) Further action Please select from drop down menu | Drop-down menu data
1 | ALUNAN MATRIK SDN BHD | Yes | To get GST registration document from supplier | Column (2) | Column (3)
2 | ASIA ITINERARY TRAVEL & TOURS S/B | Yes | To get GST registration document from supplier | Yes | Discuss with vendor/supplier for voluntary registration
3 | ASTRO RADIO SDN BHD | Yes | To get GST registration document from supplier | No | To terminate any agreement with the vendor/supplier
4 | AVION HOLIDAYS SDN BHD | Yes | To get GST registration document from supplier | Uncertain | To follow up with supplier if they will register
5 | BAGAN EIGHTEEN SDN BHD | Yes | To get GST registration document from supplier |  | To get GST registration document from supplier
6 | BENFONT ENTERPRISE | Uncertain | To follow up with supplier if they will register
7 | BON TON SDN BHD | Yes | To get GST registration document from supplier
8 | BOUSTED WELD QUAY SDN BHD | Yes | To get GST registration document from supplier
9 | BRANDING AT HEKTY SDN BHD | Uncertain | To follow up with supplier if they will register
10 | CAHAYA UTARA SDN BHD | Yes | To get GST registration document from supplier
11 | CAPITAL ONE LEISURE SDN BHD | Yes | To get GST registration document from supplier
12 | CHINA SOUTHERN AIRLINES | Yes | To get GST registration document from supplier
13 | CHING XING SPORTS AND CULTURAL CENTRE | Uncertain | To follow up with supplier if they will register
14 | CLARITY PUBLISHING SDN BHD | Uncertain | To follow up with supplier if they will register
15 | CORPORATENET SDN BHD | Yes | To get GST registration document from supplier
16 | DESIGN ARK SDN BHD | Yes | To get GST registration document from supplier
17 | DESIGN FURNITURE STATION | No | Discuss with vendor/supplier for voluntary registration
18 | DHL EXPRESS (MALAYSIA) SDN BHD | Yes | To get GST registration document from supplier
19 | DREAM RIVER VISON ENTERPRISE | Uncertain | To follow up with supplier if they will register
20 | DSOP OFFICE SYSTEM & SUPPLIES SDN BHD | Yes | To get GST registration document from supplier
21 | EASTERN & ORIENTAL HOTEL SDN BHD | Yes | To get GST registration document from supplier
22 | EASTIN HOTEL PENANG | Yes | To get GST registration document from supplier
23 | EDITORIAL ASSOCIATES | No | Discuss with vendor/supplier for voluntary registration
24 | ELITE TRANSLATIONS ASIA (M) SDN BHD | Uncertain | To follow up with supplier if they will register
25 | EMANON SDN BHD | Yes | To get GST registration document from supplier
26 | EMSOFT TRADING | Uncertain | To follow up with supplier if they will register
27 | ERNST & YOUNG TAX CONSULTANTS SDN BHD | Yes | To get GST registration document from supplier
28 | FOUR POINTS BY SHERATON PENANG | Yes | To get GST registration document from supplier
29 | FREEDOM GETAWAY ADVENTURES | Uncertain | To follow up with supplier if they will register
30 | FTZ TRAVEL & TOURS SDN BHD | Uncertain | To follow up with supplier if they will register
31 | FUJI XEROX ASIA PACIFIC PTE LTD | Uncertain | To follow up with supplier if they will register
32 | GO INTERNATIONAL GROUP SDN BHD | Uncertain | To follow up with supplier if they will register
33 | GEORGE TOWN WORLD HERITAGE INCORPORATED | Uncertain | To follow up with supplier if they will register
34 | HARPERS TRAVEL (M) SDN BHD | Uncertain | To follow up with supplier if they will register
35 | HOLIDAY TOURS & TRAVEL SDN BHD | Yes | To get GST registration document from supplier
36 | IMAGE FARM PRODUCTIONS SDN BHD | Yes | To get GST registration document from supplier
37 | IMPRESS LED ADVERTISE SDN BHD | Uncertain | To follow up with supplier if they will register
38 | ISLAMIC TOURISM CENTRE | Uncertain | To follow up with supplier if they will register
39 | JAYKODI RESOURCES | Uncertain | To follow up with supplier if they will register
40 | LA VINTAGE DESING | Uncertain | To follow up with supplier if they will register
41 | LAM AH COMPANY SDN BERHAD | Yes | To get GST registration document from supplier
42 | LEE VIDEO PRODUCTIONS SDN BHD | Uncertain | To follow up with supplier if they will register
43 | LEGION PARKING (M) SDN BHD | Uncertain | To follow up with supplier if they will register
44 | LIANG PRINTING SERVICES | Uncertain | To follow up with supplier if they will register
45 | MAGICPRINT SOLUTIONS | Uncertain | To follow up with supplier if they will register
46 | MERU UTAMA SDN BHD | Yes | To get GST registration document from supplier
47 | MSCB SYSTEM (PG) SDN BHD | Yes | To get GST registration document from supplier
48 | OMEGA SPARKLES SDN BHD | Uncertain | To follow up with supplier if they will register
49 | P.P. SETIA ENTERPRISE | Uncertain | To follow up with supplier if they will register
50 | PDC PREMIER HOLDINGS SDN BHD | Yes | To get GST registration document from supplier
51 | PENANG HERITAGE TRUST | Uncertain | To follow up with supplier if they will register
52 | PERBADANAN PEMBANGUNAN PULAU PINANG | Yes | To get GST registration document from supplier
53 | PERSATUAN PENDIDIKAN SENI PP | Uncertain | To follow up with supplier if they will register
54 | PEWTER ART TROPHY MANUFACTURES SDN BHD | Uncertain | To follow up with supplier if they will register
55 | PGCC SALES & SERVICES SDN BHD | Yes | To get GST registration document from supplier
56 | PPB GROUP BERHAD | Yes | To get GST registration document from supplier
57 | PTS TRAVEL & TOURS SDN BHD | Uncertain | To follow up with supplier if they will register
58 | R.KANESAN | Uncertain | To follow up with supplier if they will register
59 | RAPID BUS SDN BHD | Uncertain | To follow up with supplier if they will register
60 | SIN HIN BANNERS & SCRILLS SERVICES | Uncertain | To follow up with supplier if they will register
61 | STAR PUBLICATIONS (M) BERHAD | Yes | To get GST registration document from supplier
62 | STRAITS INDIGO SDN BHD | Uncertain | To follow up with supplier if they will register
63 | SYARIKAT PERCETAKAN IRISAN SDN BHD | Uncertain | To follow up with supplier if they will register
64 | TELEKOM MALAYSIA BERHAD | Yes | To get GST registration document from supplier
65 | TENAGA NASIONAL BERHAD | Yes | To get GST registration document from supplier
66 | THAI AIRWAYS INTERNATIONAL PUBLIC CO LTD | Yes | To get GST registration document from supplier
67 | THE PHOENIX PRESS SDN BHD | Uncertain | To follow up with supplier if they will register
68 | THE WELLPACK INS. SUPPLIES S/B | Uncertain | To follow up with supplier if they will register
69 | TNT EXPRESS WORLDWIDE (M) SDN BHD | Uncertain | To follow up with supplier if they will register
70 | TONG YAN TRAVEL & TOURS SDN BHD | Uncertain | To follow up with supplier if they will register
71 | TOONG LI STATIONERY & SUPPLY | Uncertain | To follow up with supplier if they will register
72 | TOP ONE DIGITAL SHOP | Uncertain | To follow up with supplier if they will register
73 | TOUR & INCENTIVE TRAVEL SDN BHD | Yes | To get GST registration document from supplier
74 | ULYSSESS WORDSTATION | Uncertain | To follow up with supplier if they will register
75 | UNI. ASIA GENERAL INSURANCE BERHAD | Yes | To get GST registration document from supplier
76 | USAINS HOLDING SDN BHD | Yes | To get GST registration document from supplier
77 | VCREATE SDN BHD | Uncertain | To follow up with supplier if they will register
78 | WEB ASP SDN BHD | Uncertain | To follow up with supplier if they will register
79 | WINSOME AIR-CONDITION ENGINEERING | Uncertain | To follow up with supplier if they will register
80 | WT LIM FOOD PRODUCTS SDN BHD | Uncertain | To follow up with supplier if they will register
81 | YNOT MUSIC STUDIO | Uncertain | To follow up with supplier if they will register
82 | YTL COMMUNICATIONS SDN BHD | Yes | To get GST registration document from supplier

## Vendor Listing
No. | SUPPLIER/VENDOR | Potential GST Registrant
|  | Yes | No | Uncertain | Estimate
1 | ALUNAN MATRIK SDN BHD | ü
2 | ASIA ITINERARY TRAVEL & TOURS S/B | ü
3 | ASTRO RADIO SDN BHD | ü |  |  | *
4 | AVION HOLIDAYS SDN BHD | ü |  |  | *
5 | BAGAN EIGHTEEN SDN BHD | ü |  |  | *
6 | BENFONT ENTERPRISE |  |  | ü
7 | BON TON SDN BHD | ü |  |  | *
8 | BOUSTED WELD QUAY SDN BHD | ü |  |  | *
9 | BRANDING AT HEKTY SDN BHD |  |  | ü
10 | CAHAYA UTARA SDN BHD | ü |  |  | *
11 | CAPITAL ONE LEISURE SDN BHD | ü |  |  | *
12 | CHINA SOUTHERN AIRLINES | ü |  |  | *
13 | CHING XING SPORTS AND CULTURAL CENTRE |  |  | ü
14 | CLARITY PUBLISHING SDN BHD |  |  | ü
15 | CORPORATENET SDN BHD | ü
16 | DESIGN ARK SDN BHD | ü |  |  | *
17 | DESIGN FURNITURE STATION |  | ü
18 | DHL EXPRESS (MALAYSIA) SDN BHD | ü
19 | DREAM RIVER VISON ENTERPRISE |  |  | ü
20 | DSOP OFFICE SYSTEM & SUPPLIES SDN BHD | ü
21 | EASTERN & ORIENTAL HOTEL SDN BHD | ü
22 | EASTIN HOTEL PENANG | ü
23 | EDITORIAL ASSOCIATES |  | ü
24 | ELITE TRANSLATIONS ASIA (M) SDN BHD |  |  | ü
25 | EMANON SDN BHD | ü |  |  | *
26 | EMSOFT TRADING |  |  | ü
27 | ERNST & YOUNG TAX CONSULTANTS SDN BHD | ü
28 | FOUR POINTS BY SHERATON PENANG | ü
29 | FREEDOM GETAWAY ADVENTURES |  |  | ü
30 | FTZ TRAVEL & TOURS SDN BHD |  |  | ü
31 | FUJI XEROX ASIA PACIFIC PTE LTD |  |  | ü
32 | GO INTERNATIONAL GROUP SDN BHD |  |  | ü
33 | GEORGE TOWN WORLD HERITAGE INCORPORATED |  |  | ü
34 | HARPERS TRAVEL (M) SDN BHD |  |  | ü
35 | HOLIDAY TOURS & TRAVEL SDN BHD | ü
36 | IMAGE FARM PRODUCTIONS SDN BHD | ü |  |  | *
37 | IMPRESS LED ADVERTISE SDN BHD |  |  | ü
38 | ISLAMIC TOURISM CENTRE |  |  | ü
39 | JAYKODI RESOURCES |  |  | ü
40 | LA VINTAGE DESING |  |  | ü
41 | LAM AH COMPANY SDN BERHAD | ü
42 | LEE VIDEO PRODUCTIONS SDN BHD |  |  | ü
43 | LEGION PARKING (M) SDN BHD |  |  | ü
44 | LIANG PRINTING SERVICES |  |  | ü
45 | MAGICPRINT SOLUTIONS |  |  | ü
46 | MERU UTAMA SDN BHD | ü
47 | MSCB SYSTEM (PG) SDN BHD | ü
48 | OMEGA SPARKLES SDN BHD |  |  | ü
49 | P.P. SETIA ENTERPRISE |  |  | ü
50 | PDC PREMIER HOLDINGS SDN BHD | ü
51 | PENANG HERITAGE TRUST |  |  | ü
52 | PERBADANAN PEMBANGUNAN PULAU PINANG | ü
53 | PERSATUAN PENDIDIKAN SENI PP |  |  | ü
54 | PEWTER ART TROPHY MANUFACTURES SDN BHD |  |  | ü
55 | PGCC SALES & SERVICES SDN BHD | ü
56 | PPB GROUP BERHAD | ü |  |  | *
57 | PTS TRAVEL & TOURS SDN BHD |  |  | ü
58 | R.KANESAN |  |  | ü
59 | RAPID BUS SDN BHD |  |  | ü
60 | SIN HIN BANNERS & SCRILLS SERVICES |  |  | ü
61 | STAR PUBLICATIONS (M) BERHAD | ü |  |  | *
62 | STRAITS INDIGO SDN BHD |  |  | ü
63 | SYARIKAT PERCETAKAN IRISAN SDN BHD |  |  | ü
64 | TELEKOM MALAYSIA BERHAD | ü
65 | TENAGA NASIONAL BERHAD | ü
66 | THAI AIRWAYS INTERNATIONAL PUBLIC CO LTD | ü
67 | THE PHOENIX PRESS SDN BHD |  |  | ü
68 | THE WELLPACK INS. SUPPLIES S/B |  |  | ü
69 | TNT EXPRESS WORLDWIDE (M) SDN BHD |  |  | ü
70 | TONG YAN TRAVEL & TOURS SDN BHD |  |  | ü
71 | TOONG LI STATIONERY & SUPPLY |  |  | ü
72 | TOP ONE DIGITAL SHOP |  |  | ü
73 | TOUR & INCENTIVE TRAVEL SDN BHD | ü
74 | ULYSSESS WORDSTATION |  |  | ü
75 | UNI. ASIA GENERAL INSURANCE BERHAD | ü |  |  | *
76 | USAINS HOLDING SDN BHD | ü |  |  | *
77 | VCREATE SDN BHD |  |  | ü
78 | WEB ASP SDN BHD |  |  | ü
79 | WINSOME AIR-CONDITION ENGINEERING |  |  | ü
80 | WT LIM FOOD PRODUCTS SDN BHD |  |  | ü
81 | YNOT MUSIC STUDIO |  |  | ü
82 | YTL COMMUNICATIONS SDN BHD | ü |  |  | *