## Readiness report
GST Issues Log | [7 empty] | STATUS
[10 empty] | Not yet started | Not Yet Started
|  |  | 06 | Price Rebalancing |  |  |  |  | Not yet started | In Progress | In Progree
[10 empty] | Done | Done
PIC: Michelle
Work Plan |  | Target Date | Completed Date | Info collected / summary of findings | Policy and Procedures (P&P) Changes (Yes /No) | Description of P&P Changes | Tool / System Changes (Yes / No) | Description of Tool / System Changes | Status / Remarks
1 | Determine transactions in which the implementation of GST may result in material savings/increase in costs | 2014-09-05 | 2014-09-05 | - Cash flow may affected in circumtances where PGT has short credit periods from supplier, this may result in PGT needing extra finances to purchase supplies | Yes | - PGT - 6% additional cost to be incurred in PGT expenses (Subject to PGT's future outcome, if the grant is exempted, not entitle for ITC) | Yes
2 | Asses impact to cost and pricing of PGT services with the introduction of GST and the repeal of sales and service tax | 2014-09-05 | 2014-09-05 | - Currently most of the suppliers/vendors does not charge SST/GST - Selling price of merchandise in TIC will be increased when GST implement | Yes | - To collect 6% of GST from customers @ TIC /PGT | Yes | - TIC's Point of Sales System to be add in a module for GST - UBS system to be upgraded to GST compliance
3 | Identify related documents to be updated / amended to quote price with GST inclusive | 2014-09-05 | 2014-09-05 | - Currently all pricing quoted/sold are excluded 6% | Yes | - To change quotation format - To added in 6% in the quotation - - Management to decide the open market value for sponsorship in return | Yes | To keep track and filing of quotation GST or non GST inclusive
4 | Determine and implement process and system change required | 2014-09-05 | 2014-09-05 | - Price quoted via email from manager | Yes | - To change the process of quotation - Account department to prepare the quotation | No | N/A
5 | Ensure that pricing decisions based on these transaction are justifiable by PGT | 2014-09-05 | 2014-09-05 | - Pricing of merchandise will be based on 6% from supplier | Yes | - To added 6% for every merchandise (If PGT register with GST) | Yes | To track the GST output tax and filing
6 | Ensure documents are retained in order to justify pricing decisions | 2014-09-05 | 2014-09-05 | - Invoice with 6% GST from supplier | Yes | - To claim input tax for tax supplies in TIC - To claim input tax for PGT expenses | Yes | To keep track and filing invoices and quotation from supplier differently
7 | If necessary, consider getting legal advice in respect of adherence to the Price Control & Anti -Profiteering Act 2011 | 2014-09-05 | 2014-09-05 | - Currently did not engage any legal firm | Yes | - To get legal advice from legal firm/PDC legal department | No | N/A
8 | Communicate price changes to stakeholders, distributors and customers | 2014-09-05 | 2014-09-05 | - Currently no body | Yes | - Staff should be educated and communicate to tourists / customers | No | N/A
9 | Educate & train sales personnel on the new pricing structure | 2014-09-05 | 2014-09-05 | - Currently no body | Yes | - To discuss with deparment head for training | No | N/A