## GST Checklist-PDCPH
PDC PREMIER HOLDINGS SDN BHD GST WORK PLAN CHECKLIST | [8 empty] | Not yet started
In Progress
Done
Project Lead: Puan Vasandi Subramaniam
Category | List of Issues Log |  | PIC | Targeted Month | Target Date | Completed Date | Status | Remarks
A | GST 01 | Strategic: Budgeting and Resource Requirement for GST Implementation | Puan Vasandi Subramaniam | August |  |  | Not yet started
A | GST 03 | Strategic: Preferred vendor management | Puan Indah |  |  |  | Not yet started
A | GST 04 | Strategic : Price Rebalancing | Puan Sangeetha |  |  |  | Not yet started
A | GST 28 | Transitional: Inclusion of GST clause in all contracts | Puan Vasandi/Puan Juliana |  |  |  | Not yet started
B | GST 09 | Compliance: Time of Supply | Puan Sangeetha/Puan Juliana | September and October |  |  | Not yet started
B | GST 10 | Compliance: Sundry income and Miscellaneous Expenditure | Puan Sangeetha |  |  |  | Not yet started
B | GST 15 | Compliance: Blocked Input Tax | Puan Sangeetha/Puan Juliana |  |  |  | Not yet started
B | GST 16 | Compliance: Entertainment expenditure | Puan Sangeetha |  |  |  | Done
B | GST 17 | Compliance: Employee Benefits | Puan Vasandi/Puan Sangeetha |  |  |  | In Progress
B | GST 18 | Compliance: Reimbursement of staff expenses/claims | Puan Vasandi/Puan Sangeetha |  |  |  | Not yet started
B | GST 19 | Compliance: Goods provided for free | Puan Vasandi/Puan Sangeetha |  |  |  | Not yet started
B | GST 23 | Compliance: Disposal of fixed assets | Puan Indah/Puan Sangeetha |  |  |  | Not yet started
B | GST 24 | Compliance: Sponsorship | Puan Vasandi/Puan Sangeetha |  |  |  | Not yet started
B | GST 25 | Compliance: Payments to Federal & State Governments, Statutory Bodies and Local Authorities | Cik Swaran/Puan Sangeetha |  |  |  | Not yet started
C | GST 11 | Compliance: De Minimis and Incidental Financial Supplies | Puan Sangeetha | September and October |  |  | Not yet started
C | GST 12 | Compliance: Apportionment of 'Indirect Costs' for Recovery of Input Tax | Puan Sangeetha |  |  |  | Not yet started
C | GST 21 | Compliance: Inter-company Supplies and Cross Charges to Related Entities | Puan Sangeetha/Puan Juliana |  |  |  | Not yet started
C | GST 22 | Compliance: Open Market Value ("OMV") | Puan Sangeetha/Puan Juliana |  |  |  | Not yet started
D | GST 05 | Compliance: Tax coding for GST | Puan Sangeetha/Puan Juliana | September and October |  |  | Not yet started
D | GST 07 | Compliance: Issuance of Tax Invoices | Puan Sangeetha |  |  |  | Not yet started
D | GST 08 | Compliance: GST Adjustments to Tax Invoices with Credit and Debit Notes | Puan Sangeetha |  |  |  | Not yet started
D | GST 14 | Compliance: Accounting recognition vs GST recognition for input tax claim | Puan Sangeetha/Puan Juliana |  |  |  | Not yet started
E | GST 06 | Compliance: Record keeping requirements for GST purposes | Puan Sangeetha/Puan Juliana | November |  |  | Not yet started
E | GST 13 | Compliance: Documentation to Claim Input Tax Credit | Puan Sangeetha |  |  |  | Not yet started
E | GST 20 | Compliance: Reimbursement vs disbursement | Puan Vasandi/Puan Sangeetha |  |  |  | Not yet started
E | GST 26 | Compliance: GST Relief for Bad Debts | Puan Sangeetha/Puan Juliana |  |  |  | Not yet started
F | GST 02 | Strategic: CAPEX | Puan Sangeetha | December to March |  |  | Not yet started
F | GST 27 | Transitional: Cancellation of Your Service Tax License | Puan Vasandi |  |  |  | Not yet started
F | GST 29 | Transitional : Contracts spanning GST start date | Puan Sangeetha/Puan Juliana/ Puan Vasandi |  |  |  | Not yet started

## Readiness report
GST Issues Log | [7 empty] | STATUS
[10 empty] | Not yet started | Not Yet Started
|  |  | 10 | Time of Supply |  |  |  |  | In Progress | In Progress | In Progree
[10 empty] | Done | Done
PIC: Michelle
Work Plan |  | Target Date | Completed Date | Info collected / summary of findings | Policy and Procedures (P&P) Changes (Yes /No) | Description of P&P Changes | Tool / System Changes (Yes / No) | Description of Tool / System Changes | Status / Remarks
1 | Establish processes to account for GST at the Basic Tax Point (BTP) | 2014-09-05 | 2014-09-05 | 2 type of sales - Cash and credit term | Yes | To keep track the GST filiing date based on ATP | No | N/A
a | For supplies of all goods and services, the BTP is taken to be : i) Goods sold by PGT - date the goods are " made available" to receipient | 2014-09-05 | 2014-09-05 | - Issuance of receipt for cash sales - Issuance of Invoice for credit term | No | N/A | Yes | Issuance of tax invoice for both
|  |  |  | * Tours - tourist pay in advance to book the tour, we collect money in advance to secure the date and book for tour guide | ?? | Please advise to follow which date BTP or ATP
| ii) Services - date when the service is performed, and | 2014-09-05 | 2014-09-05 | - Received invoice after services performed | Yes | To keep track of the invoice receive, must be within 21 days | Yes | To file for GST input tax return
| iii) Disposal/transfer of business assets (date when goods are transferred/disposed of) | 2014-09-05 | 2014-09-05 | Currently no process | Yes | To date the assets been transferred / disposal | Yes | To issue tax invoice & and account for GST
2 | Establish processes to identify when BTP is overridden by Actual Tax Point (ATP) | 2014-09-05 | 2014-09-05 | Currently no process | Yes | Refer to flow chart (sales, expenses and consignment sales) | Yes | To issue tax invoice and file for GST
3 | Decide on policy whether to take advantage of the 21-day rule from BTP | 2014-09-05 | 2014-09-05 | Cash term - based on ATP (when payment received) Credit term - to use 21 days rule | Yes | To ensure invoice issue within 21 days To ensure invoice from supplier receive in 21 days
a | If yes, establish policy to issue tax invoice within 21 days after BTP (provided payment is not received before the BTP) | 2014-09-05 | 2014-09-05 | To establish policy , issue tax invoice within 21 days for credit terms * Tours - payment receive in advance |  | Please advise to follow which date BTP or ATP
b | Ensure tax invocing is triggered by processed/approved service order within 21 days, and | 2014-09-05 | 2014-09-05 | Currently invoice is issued within 21 days Invoice from supplier may be delay after BTP | Yes | To inform supplier to issue tax invoice within 21 days | No | N/A
c | Identify any instances where you may wish to apply to the DG to be granted an extension of the 21-day rule (monthly or quarterly unit holder/policyholder statements) |  |  | No
4 | Identify instances when advance payments/deposits do not create a tax point Eg. security deposits such as your collateral "bond" receipts which are not treated as a payment received by you. It will also include refundable deposits and deposits forfeited to compensate you for loss or damages |  |  | - Advance payment to supplier - Advance payment received from customers |  | Please advise to follow which date BTP or ATP
5 | Seek clarification, when required, of " date payment received" for various modes of payment: i) Book-entries ii) Cash receipts iii) Direct debit/credit and receipts/standing orders iv) Telegraphic Transfer v) Cheques vi) Payment via internet banking | 2014-09-05 | 2014-09-05 | - book entries based on date payment received and bank in - Payment received advance from tourist for tour booking | No | N/A | No | N/A
6 | Put in place processes and system to monitor the trigger point for time of supply and ensure GST is accounted for appropriately | 2014-09-05 | 2014-09-05 | - A process and system to monitor GST is accounted to be prepared | Yes | A process flow | No | N/A
7 | Review listing of all services provided and identify these that qualify as continuous services | 2014-09-05 | 2014-09-05 | - Selling of merchandise, tours & consignment products (Continuous service) - Payment receive in advance for tour booking (continuous service) | No | N/A | No | N/A
8 | Establish policy and processes to account for GST correctly on contnuous services | 2014-09-05 | 2014-09-05 | - To prepare a process & policy for continous services | Yes | A new policy and process | No | N/A
9 | Communicate policies and processes to relevant staff | 2014-09-05 | 2014-09-05 | - Currently no body | Yes | To discuss with head of department on policies and process | No | N/A
Note 1 : the above must also apply to zero rated and exempt supplies made by you as you are required to account/report these in your GST return
Note 2 : For imported services, the tax point is the date payment is made

## Time of Supply - Sales
(Sales) Basic Tax Point - PGT/TIC
YES
Goods sold in TIC
Payment received or tax invoice issued before the BTP
YES
Actual Tax Point (ATP) Payment received in Cash & goods are made available to customers/recipient
Tax invoice issued within 21 days after BTP?
NO
Actual Tax Point (ATP) Date of issuance of tax invoice
Basic Tax Point
NO
Basic Tax Point (BTP)

## Time of Supply - Invoice Rcd
(Expenses) Basic Tax Point - PGT/TIC
Payment done or tax invoice issued before the BTP
YES
Actual Tax Point (ATP) Payment paid in cash / Paid in advance as deposit upon reciving of tax invoice
Tax invoice received within 21 days of BTP?
NO
Actual Tax Point (ATP) Tax invoice date? or date receive of tax invoice??
Basic Tax Point
Basic Tax Point (BTP)
* Goods received
* Service performed
*Disposal /transfered of Business assets
YES
NO

## Time of Supply - Consignment
(Consignment) Basic Tax Point - PGT/TIC
End of the month closing of sales
Basic Tax Point (BTP)
Consignor supplied goods to TIC ("consignee")
Consignee issue statement of sales to consignor to inform quantity of goods sold
Actual Tax Point
Consignor issue an invoice to TIC on actual number of goods sold
(21 days from the date of receipt of the statement of sales)
After 12 months, the remaining stock had not been sold, the consignor needs to issue a tax invoice within 21 days after the 12 months period has lapsed?