## GST Checklist-PDCPH
PDC PREMIER HOLDINGS SDN BHD GST WORK PLAN CHECKLIST | [8 empty] | Not yet started
In Progress
Done
Project Lead: Puan Vasandi Subramaniam
Category | List of Issues Log |  | PIC | Targeted Month | Target Date | Completed Date | Status | Remarks
A | GST 01 | Strategic: Budgeting and Resource Requirement for GST Implementation | Puan Vasandi Subramaniam | August |  |  | Not yet started
A | GST 03 | Strategic: Preferred vendor management | Puan Indah |  |  |  | Not yet started
A | GST 04 | Strategic : Price Rebalancing | Puan Sangeetha |  |  |  | Not yet started
A | GST 28 | Transitional: Inclusion of GST clause in all contracts | Puan Vasandi/Puan Juliana |  |  |  | Not yet started
B | GST 09 | Compliance: Time of Supply | Puan Sangeetha/Puan Juliana | September and October |  |  | Not yet started
B | GST 10 | Compliance: Sundry income and Miscellaneous Expenditure | Puan Sangeetha |  |  |  | Not yet started
B | GST 15 | Compliance: Blocked Input Tax | Puan Sangeetha/Puan Juliana |  |  |  | Not yet started
B | GST 16 | Compliance: Entertainment expenditure | Puan Sangeetha |  |  |  | Done
B | GST 17 | Compliance: Employee Benefits | Puan Vasandi/Puan Sangeetha |  |  |  | In Progress
B | GST 18 | Compliance: Reimbursement of staff expenses/claims | Puan Vasandi/Puan Sangeetha |  |  |  | Not yet started
B | GST 19 | Compliance: Goods provided for free | Puan Vasandi/Puan Sangeetha |  |  |  | Not yet started
B | GST 23 | Compliance: Disposal of fixed assets | Puan Indah/Puan Sangeetha |  |  |  | Not yet started
B | GST 24 | Compliance: Sponsorship | Puan Vasandi/Puan Sangeetha |  |  |  | Not yet started
B | GST 25 | Compliance: Payments to Federal & State Governments, Statutory Bodies and Local Authorities | Cik Swaran/Puan Sangeetha |  |  |  | Not yet started
C | GST 11 | Compliance: De Minimis and Incidental Financial Supplies | Puan Sangeetha | September and October |  |  | Not yet started
C | GST 12 | Compliance: Apportionment of 'Indirect Costs' for Recovery of Input Tax | Puan Sangeetha |  |  |  | Not yet started
C | GST 21 | Compliance: Inter-company Supplies and Cross Charges to Related Entities | Puan Sangeetha/Puan Juliana |  |  |  | Not yet started
C | GST 22 | Compliance: Open Market Value ("OMV") | Puan Sangeetha/Puan Juliana |  |  |  | Not yet started
D | GST 05 | Compliance: Tax coding for GST | Puan Sangeetha/Puan Juliana | September and October |  |  | Not yet started
D | GST 07 | Compliance: Issuance of Tax Invoices | Puan Sangeetha |  |  |  | Not yet started
D | GST 08 | Compliance: GST Adjustments to Tax Invoices with Credit and Debit Notes | Puan Sangeetha |  |  |  | Not yet started
D | GST 14 | Compliance: Accounting recognition vs GST recognition for input tax claim | Puan Sangeetha/Puan Juliana |  |  |  | Not yet started
E | GST 06 | Compliance: Record keeping requirements for GST purposes | Puan Sangeetha/Puan Juliana | November |  |  | Not yet started
E | GST 13 | Compliance: Documentation to Claim Input Tax Credit | Puan Sangeetha |  |  |  | Not yet started
E | GST 20 | Compliance: Reimbursement vs disbursement | Puan Vasandi/Puan Sangeetha |  |  |  | Not yet started
E | GST 26 | Compliance: GST Relief for Bad Debts | Puan Sangeetha/Puan Juliana |  |  |  | Not yet started
F | GST 02 | Strategic: CAPEX | Puan Sangeetha | December to March |  |  | Not yet started
F | GST 27 | Transitional: Cancellation of Your Service Tax License | Puan Vasandi |  |  |  | Not yet started
F | GST 29 | Transitional : Contracts spanning GST start date | Puan Sangeetha/Puan Juliana/ Puan Vasandi |  |  |  | Not yet started

## Readiness report
GST Issues Log | [6 empty] | STATUS
[9 empty] | Not yet started | Not Yet Started
[8 empty] | Not yet started | In Progress | In Progree
[9 empty] | Done | Done
PIC:
Work Plan | Target Date | Completed Date | Info collected / summary of findings | Policy and Procedures (P&P) Changes (Yes /No) | Description of P&P Changes | Tool / System Changes (Yes / No) | Description of Tool / System Changes | Status / Remarks
1
2
3
4
5
6
7