## Summary
GST WORK PLAN (SUMMARY)
[5 empty] | JULIANA |  |  | SABARUL |  |  | KIM
| SYSTEM |  |  |  | UBS | WIZ | UBS | UBS |  |  | UBS | QNE | IFCA
No | GROUP | CATEGORY |  | WORKPLAN | PDCPH | PDCP | PDCN | PDCC | IGP | PIHH | PGT | TELCO | SU | Target Date
[5 empty] | GST NO | GST NO | GST NO | GST NO | GST NO | GST NO | GST NO | GST NO | GST NO
1 |  | A | Strategic | Budgeting and Resource Requirement for GST Implementation | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 2014-09-04
2 | Contract | A | Transitional | Inclusion of GST Clause In All Contracts / Agreements | 28 | 41 | 34 | 33 | 15 |  |  | 31 | 29 | 2014-09-04
3 | Creditors | A | Strategic | Preferred Vendor Management | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 3 | 3 | 2014-09-04 | Legend:
4 | Income | A | Strategic | Price Rebalancing | 4 | 4 | 4 | 4 |  |  | 6 | 4 | 4 | 2014-09-04 |  | Readiness Rpt submitted
5 |  | A | Compliance | Classification of land titles |  | 11 | [7 empty] | 2014-09-04
6 | Income | B | Compliance | Time of Supply | 9 | 9 | 9 | 9 | 8 | 8 | 10 | 9 | 9 | 2014-09-04
7 | Income | B | Compliance | Sale of tender documents |  |  | 10 | 10 | [5 empty] | 2014-09-04
8 | Income | B | Compliance | Accounting for GST - sale of property |  | 10 | [7 empty] | 2014-09-04
9 | Debtors | B | Compliance | Advance and Deposit Receipts |  | 12 | 11 | 11 |  | 9 |  | 10 | 10 | 2014-09-04
10 | Income | B | Compliance | Other Income and Misc Expenditure | 10 | 13 | 12 | 12 | 9 | 10 | 12 | 11 | 11 | 2014-09-11
11 | Exp-Staff | B | Compliance | Blocked Input Tax | 15 | 24 | 18 | 18 |  | 16 | 17 | 17 | 16 | 2014-09-11
12 | Exp-Staff | B | Compliance | Entertainment Expenditures | 16 | 25 | 19 | 19 |  | 17 | 18 | 18 | 17 | 2014-09-11
13 | Exp-Staff | B | Compliance | Employee Benefits | 17 | 26 | 20 | 20 |  | 18 | 19 | 19 | 18 | 2014-09-11
14 | Exp-Staff | B | Compliance | Reimbursement of Staff Expenses/Claims | 18 | 27 | 21 | 21 |  | 19 | 20 | 20 | 21 | 2014-09-11
15 | Exp-free | B | Compliance | Goods Provided for Free | 19 | 28 | 22 | 22 |  | 20 | 21 | 21 | 20 | 2014-09-11
16 | Exp-free | B | Compliance | Free Services | [5 empty] | 21 | 22 |  |  | 2014-09-11
17 | Exp | B | Compliance | Sponsorship / Donation | 24 | 37 | 31 | 28 |  | 23 | 26 | 28 |  | 2014-09-18
18 | Income | B | Compliance | Penalties, Compensation & Damages Receipt | 25 | [6 empty] | 25 |  | 2014-09-18
19 | Exp | B | Compliance | Payments to Federal & State Governments, Statutory Bodies and Local Authorities |  | 38 | 32 | 29 |  | 24 | 27 | 29 | 26 | 2014-09-18
20 | Income | B | Compliance | Commission Received | [6 empty] | 11 |  |  | 2014-09-18
21 | Debtors | B | Compliance | GST Relief for Bad Debts | 26 | 39 | 33 | 31 |  |  |  | 30 | 27 | 2014-09-18
22 |  | B | Compliance | Transfer of amenities, infrastructure |  | 19 | [7 empty] | 2014-09-18
23 |  | B | Compliance | Sale & marketing of property |  | 22 | [7 empty] | 2014-09-18
24 |  | B | Compliance | Mixed development project expenses |  | 23 | [7 empty] | 2014-09-18
25 |  | B | Compliance | Insurance compensation |  |  | 17 | [6 empty] | 2014-09-25
26 |  | B | Compliance | Forfeiture/cancellation fees/penalties received and paid |  | 32 | 26 | [6 empty] | 2014-09-25
27 |  | B | Compliance | Out of courts settlements |  | 33 | 27 | [6 empty] | 2014-09-25
28 | FA | B | Compliance | Disposal of Fixed Assets | 23 | 34 | 28 | 26 | 14 | 22 | 23 | 26 | 24 | 2014-09-25
29 | Income | B | Compliance | Sale of show house and car park |  | 35
30 | Exp-oversea | B | Compliance | GST on Importation of Goods |  |  |  | 35 |  | 14 |  | 16 |  | 2014-09-25
31 | Exp-oversea | B | Compliance | Imported Services (Reverse Charge) |  |  |  | 17 |  | 15 | 16 |  |  | 2014-09-25
32 | Exp-oversea | B | Compliance | GST / VAT Incurred Overseas |  |  |  | 30 |  | 25 | 28 |  |  | 2014-09-25
33 | Income | C | Compliance | De Minimis and Incidental Financial Supplies | 11 | 14 | 13 | 13 | 10 | 11 | 13 | 12 | 12 | 2014-09-25
34 | Exp | C | Compliance | Apportionment of 'Indirect Costs' for Recovery of Input Tax | 12 | 15 | 14 | 14 |  |  |  | 13 | 13 | 2014-09-25
35 |  | C | Compliance | Direct allocation for recovery of input tax |  | 16 | [7 empty] | 2014-09-25
36 |  | C | Compliance | Annual adjustment of residual input tax |  | 17 | [7 empty] | 2014-10-02
37 | Exp | C | Compliance | Inter-Company Supplies and Cross Charges to related entities | 21 | 30 | 24 | 24 |  |  |  | 23 | 22 | 2014-10-02
38 | FA | C | Compliance | Open Market Value ("OMV") | 22 | 31 | 25 | 25 |  |  |  | 24 | 23 | 2014-10-02
39 | System | D | Compliance | Tax Coding for GST | 5 | 5 | 5 | 5 | 5 | 5 | 7 | 5 | 5 | 2014-10-02
40 | Income | D | Compliance | Issuance of Tax Invoices | 7 | 7 | 7 | 7 | 7 | 7 | 9 | 7 | 7 | 2014-10-02
41 | Income | D | Compliance | GST Adjustments to Tax Invoices With Credit and Debit Notes | 8 | 8 | 8 | 8 |  |  |  | 8 | 8 | 2014-10-02
42 | Creditors | D | Compliance | Accounting Recognition vs GST Recognition for Input Tax Claim | 14 | 21 | 16 | 16 | 12 | 13 | 15 | 15 | 15 | 2014-10-09
43 | Creditors | E | Compliance | Record Keeping Requirements for GST Purposes | 6 | 6 | 6 | 6 | 6 | 6 | 8 | 6 | 6 | 2014-10-09
44 |  | E | Compliance | High value caoital goods |  | 18 | [7 empty] | 2014-10-09
45 | Creditors | E | Compliance | Documentation to Claim Input Tax Credit | 13 | 20 | 15 | 15 | 11 | 12 | 14 | 14 | 14 | 2014-10-09
46 | Exp | E | Compliance | Reimbursement vs Disbursement | 20 | 29 | 23 | 23 | 13 |  |  | 22 | 19 | 2014-10-09
47 | FA | E | Compliance | GST on Lost/Destroyed/Stolen/Obsolete Stock |  |  | 29 |  |  |  | 24 |  |  | 2014-10-09
48 | FA | E | Compliance | Company Cars |  | 36 | 30 | 27 |  |  | 25 | 27 | 25 | 2014-10-16
49 |  | E | Compliance | Valuing work in progress for development project |  | 43 | [7 empty] | 2014-10-16
50 | Registration | E | Compliance | Approved Tourist Refund Scheme Outlet | [6 empty] | 5 |  |  | 2014-10-16
51 | FA | F | Strategic | CAPEX | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 2 | 2 | 2014-10-16
52 | Debtors | F | Transitional | Cancellation Of your Service tax License | 27 | 40 |  | 32 |  |  |  |  | 28 | 2014-10-16
53 | Contract | F | Transitional | Contract Spanning GST Start Date | 29 | 42 | 35 | 34 | 16 |  |  | 32 | 30 | 2014-10-16
54 | Registration |  | Strategic | Registration For GST |  |  |  |  | 1 | 1 | 1 |  |  | 2014-10-16
55
|  |  |  | Count | 29 | 43 | 35 | 35 | 16 | 25 | 28 | 32 | 30

## GST Checklist-PDCPH
PDC PREMIER HOLDINGS SDN BHD GST WORK PLAN CHECKLIST | [8 empty] | Not yet started
In Progress
Done
Project Lead: Puan Vasandi Subramaniam
Category | List of Issues Log |  | PIC | Targeted Month | Target Date | Completed Date | Status | Remarks
A | GST 01 | Strategic: Budgeting and Resource Requirement for GST Implementation | Puan Vasandi Subramaniam | August | 2014-08-29 |  | Not yet started
A | GST 28 | Transitional: Inclusion of GST clause in all contracts | Puan Vasandi/Puan Juliana |  |  |  | Not yet started
A | GST 03 | Strategic: Preferred vendor management | Puan Indah | September | 2014-09-04 |  | Not yet started
A | GST 04 | Strategic : Price Rebalancing | Puan Indah |  |  |  | Not yet started
B | GST 09 | Compliance: Time of Supply | Puan Indah/Puan Juliana |  |  |  | Not yet started
B | GST 10 | Compliance: Sundry income and Miscellaneous Expenditure | Puan Indah |  | 2014-09-11 |  | Not yet started
B | GST 15 | Compliance: Blocked Input Tax | Puan Indah/Puan Juliana |  |  |  | Not yet started
B | GST 16 | Compliance: Entertainment expenditure | Puan Indah |  |  |  | Done
B | GST 17 | Compliance: Employee Benefits | Puan Vasandi/Puan Indah |  |  |  | In Progress
B | GST 18 | Compliance: Reimbursement of staff expenses/claims | Puan Vasandi/Puan Indah |  |  |  | Not yet started
B | GST 19 | Compliance: Goods provided for free | Puan Vasandi/Puan Indah |  |  |  | Not yet started
B | GST 24 | Compliance: Sponsorship | Puan Vasandi/Puan Indah |  | 2014-09-18 |  | Not yet started
E | GST 26 | Compliance: GST Relief for Bad Debts | Puan Indah/Puan Juliana |  |  |  | Not yet started
B | GST 25 | Compliance: Payments to Federal & State Governments, Statutory Bodies and Local Authorities | Cik Swaran/Puan Sangeetha |  |  |  | Not yet started
C | GST 11 | Compliance: De Minimis and Incidental Financial Supplies | Puan Indah |  | 2014-09-25 |  | Not yet started
B | GST 23 | Compliance: Disposal of fixed assets | Puan Indah |  |  |  | Not yet started
C | GST 12 | Compliance: Apportionment of 'Indirect Costs' for Recovery of Input Tax | Puan Indah |  |  |  | Not yet started
C | GST 21 | Compliance: Inter-company Supplies and Cross Charges to Related Entities | Puan Indah/Puan Juliana | October | 2014-10-02 |  | Not yet started
C | GST 22 | Compliance: Open Market Value ("OMV") | Puan Indah/Puan Juliana |  |  |  | Not yet started
D | GST 05 | Compliance: Tax coding for GST | Puan Indah/Puan Juliana |  |  |  | Not yet started
D | GST 07 | Compliance: Issuance of Tax Invoices | Puan Indah |  |  |  | Not yet started
D | GST 08 | Compliance: GST Adjustments to Tax Invoices with Credit and Debit Notes | Puan Indah |  |  |  | Not yet started
D | GST 14 | Compliance: Accounting recognition vs GST recognition for input tax claim | Puan Indah/Puan Juliana |  | 2014-10-09 |  | Not yet started
E | GST 06 | Compliance: Record keeping requirements for GST purposes | Puan Indah/Puan Juliana |  |  |  | Not yet started
E | GST 13 | Compliance: Documentation to Claim Input Tax Credit | Puan Indah |  |  |  | Not yet started
E | GST 20 | Compliance: Reimbursement vs disbursement | Puan Vasandi/Puan Indah |  |  |  | Not yet started
F | GST 02 | Strategic: CAPEX | Puan Indah |  | 2014-10-16 |  | Not yet started
F | GST 27 | Transitional: Cancellation of Your Service Tax License | Puan Vasandi |  |  |  | Not yet started
F | GST 29 | Transitional : Contracts spanning GST start date | Puan Indah/Puan Juliana/ Puan Vasandi |  |  |  | Not yet started

## GST Checklist-PDCP
PDC PROPERTIES SDN BHD GST WORK PLAN CHECKLIST | [8 empty] | Not yet started
In Progress
Done
Project Lead: Izman Haris
Category | List of Issues Log |  | PIC | Targeted Month | Target Date | Completed Date | Status | Remarks
A | GST 01 | Strategic: Budgeting and Resource Requirement for GST Implementation | Izman | August | 2014-08-29 |  | Not yet started
A | GST 41 | Transitional: Inclusion of GST clause in all contracts | Norsuriati |  |  |  | In Progress
A | GST 03 | Strategic: Preferred vendor management | Izman | September | 2014-09-04 |  | Not yet started
A | GST 04 | Strategic : Price Rebalancing | June |  |  |  | Not yet started
A | GST 11 | Compliance: Classification of Land Titles | Zuraida |  |  |  | Not yet started
B | GST 09 | Compliance: Time of Supply | Izman |  |  |  | Not yet started
B | GST 10 | Compliance: Accounting for GST - Sale of Property | Ang |  |  |  | Not yet started
B | GST 12 | Compliance: Advance and Deposit Receipts | Ang |  |  |  | Done
B | GST 13 | Compliance: Sundry income and Miscellaneous Expenditure | <PENDING> | September | 2014-09-11 |  | In Progress
B | GST 24 | Compliance: Blocked Input Tax | <PENDING> |  |  |  | Not yet started
B | GST 25 | Compliance: Entertainment expenditures | Izman |  |  |  | Not yet started
B | GST 26 | Compliance: Employee Benefits | Izman |  |  |  | Not yet started
B | GST 27 | Compliance: Reimbursement of staff expenses/claims | <PENDING> |  |  |  | Not yet started
B | GST 28 | Compliance: Goods provided for free | Izman |  |  |  | Not yet started
B | GST 37 | Compliance: Sponsorship | <PENDING> | September | 2014-09-18 |  | Not yet started
B | GST 38 | Compliance: Payments to Federal & State Governments, Statutory Bodies and Local Authorities | Zuraida |  |  |  | In Progress
B | GST 39 | Compliance: GST Relief for Bad Debts | Izman |  |  |  | Not yet started
B | GST 19 | Compliance: Transfer of Amenities, Infrastructure | Risma |  |  |  | Not yet started
B | GST 22 | Compliance: Sales & Marketing of Property | Ang |  |  |  | Not yet started
B | GST 23 | Compliance: Mixed Development Project Expenses | June |  |  |  | Not yet started
B | GST 32 | Compliance: Forfeiture / Cancellation Fees and Penalties Received | Ang | September | 2014-09-25 |  | Not yet started
B | GST 33 | Compliance: Out of Court Settlements | Ang |  |  |  | Not yet started
B | GST 34 | Compliance: Disposal of fixed assets | Izman |  |  |  | Not yet started
B | GST 35 | Compliance: Sale of Show House and Car Park | Ang |  |  |  | Not yet started
C | GST 14 | Compliance: De minimis and Incidental Financial Supplies | Izman |  |  |  | Not yet started
C | GST 15 | Compliance: Apportionment of 'Indirect Costs' for Recovery of Input Tax | Izman |  |  |  | Not yet started
C | GST 16 | Compliance: Direct Allocation for Recovery of Input Tax | Izman |  |  |  | Not yet started
C | GST 17 | Compliance: Annual adjustment of residual input tax | Izman | October | 2014-10-02 |  | Not yet started
C | GST 30 | Compliance: Inter-company Supplies and Cross Charges to Related Entities | June |  |  |  | Not yet started
C | GST 31 | Compliance: Open Market Value ("OMV") | Izman |  |  |  | Not yet started
D | GST 05 | Compliance: Tax coding for GST | <PENDING> |  |  |  | Not yet started
D | GST 07 | Compliance: Issuance of Tax Invoices | Izman |  |  |  | Not yet started
D | GST 08 | Compliance: GST Adjustments to Tax Invoices with Credit and Debit Notes | Izman |  |  |  | Not yet started
D | GST 21 | Compliance: Accounting recognition vs GST recognition for input tax claim | Izman | October | 2014-10-09 |  | Not yet started
E | GST 06 | Compliance: Record keeping requirements for GST purposes | Izman |  |  |  | Not yet started
E | GST 18 | Compliance: High Value Capital Goods | Izman |  |  |  | Not yet started
E | GST 20 | Compliance: Documentation to Claim Input Tax Credit | Izman |  |  |  | Not yet started
E | GST 29 | Compliance: Reimbursement vs disbursement | June |  |  |  | Not yet started
E | GST 36 | Compliance: Company cars | Izman | October | 2014-10-16 |  | Not yet started
E | GST 43 | Compliance: Valuing Work In Progress for Development Projects | Norsuriati |  |  |  | Not yet started
F | GST 02 | Strategic: CAPEX | Izman |  |  |  | Not yet started
F | GST 40 | Transitional: Cancellation of Your Service Tax License | <PENDING> |  |  |  | Not yet started
F | GST 42 | Transitional : Contracts spanning GST start date | Norsuriati |  |  |  | Not yet started

## GST Checklist- PDCN
PDC NUSABINA SDN BHD GST WORK PLAN CHECKLIST | [8 empty] | Not yet started
In Progress
Done
Project Lead: A'ida
Category | List of Issues Log |  | PIC | Targeted Month | Target Date | Completed Date | Status | Remarks
A | GST01 | Strategic: Budgeting and Resource Requirement for GST Implementation | A'ida | August | 2014-08-29 |  | Not yet started
A | GST34 | Transitional: Inclusion of GST clause in all contracts | A'ida/Faiz |  |  |  | Done
A | GST03 | Strategic: Preferred vendor management | Faiz | September | 2014-09-04 |  | Not yet started
A | GST04 | Strategic: Price Rebalancing | Faiz |  |  |  | In Progress
B | GST09 | Compliance: Time of Supply | Faiz |  |  |  | Not yet started
B | GST10 | Compliance: Sale of Tender Documents | Faiz |  |  |  | Not yet started
B | GST11 | Compliance: Advance and Deposit Receipts | A'ida |  |  |  | Not yet started
B | GST12 | Compliance: Sundry income and Miscellaneous Expenditure | A'ida | September | 2014-09-11 |  | Not yet started
B | GST18 | Compliance: Blocked Input Tax | A'ida |  |  |  | In Progress
B | GST19 | Compliance: Entertainment expenditures | A'ida |  |  |  | Not yet started
B | GST20 | Compliance: Employee Benefits | A'ida/Nasir |  |  |  | Not yet started
B | GST21 | Compliance: Reimbursement of staff expenses/ claims | A'ida |  |  |  | Not yet started
B | GST22 | Compliance: Goods provided for free | A'ida/Nasir |  |  |  | Not yet started
B | GST28 | Compliance: Disposal of fixed assets | A'ida | September | 2014-09-18 |  | Not yet started
B | GST31 | Compliance: Sponsorship / Donation | A'ida |  |  |  | Not yet started
B | GST32 | Compliance: Payments to Federal & State Governments, Statutory Bodies and Local Authorities | A'ida/Nasir/Faiz |  |  |  | Not yet started
E | GST33 | Compliance: GST Relief for Bad Debts | A'ida/Nasir |  |  |  | Not yet started
B | GST17 | Compliance: Insurance compensation | A'ida/Nasir | September | 2014-09-25 |  | Not yet started
B | GST14 | Compliance: Apportionment of 'Indirect Costs' for Recovery of Input Tax | A'ida/Faiz |  |  |  | Not yet started
B | GST27 | Compliance: Out of Court Settlements | A'ida/Nasir |  |  |  | Not yet started
B | GST13 | Compliance: De minimis and Incidental Financial Supplies | A'ida |  |  |  | Not yet started
B | GST26 | Compliance: Forfeiture / Cancellation Fees / Penalties received and paid | A'ida/Faiz |  |  |  | Not yet started
D | GST07 | Compliance: Issuance of Tax Invoices | A'ida | October | 2014-10-02 |  | Not yet started
C | GST24 | Compliance: Inter-Company Supplies and Cross Charges to Related Entities | A'ida |  |  |  | Not yet started
C | GST25 | Compliance: Open Market Value ("OMV") | A'ida/Faiz |  |  |  | In Progress
D | GST05 | Compliance: Tax coding for GST | A'ida |  |  |  | Not yet started
D | GST08 | Compliance: GST Adjustments to Tax Invoices with Credit and Debit Notes | A'ida |  |  |  | Not yet started
B | GST15 | Compliance: Documentation to Claim Input Tax Credit | A'ida | October | 2014-10-09 |  | Not yet started
B | GST16 | Compliance: Accounting recognition vs GST recognition for input tax claim | A'ida |  |  |  | Not yet started
E | GST06 | Compliance: Record keeping requirements for GST purposes | A'ida / Faiz |  |  |  | Not yet started
E | GST23 | Compliance: Reimbursement vs Disbursement | A'ida |  |  |  | Not yet started
E | GST29 | Compliance: GST on Lost/ Destroyed/ Stolen/ Obsolete Stock | A'ida |  |  |  | Not yet started
E | GST30 | Compliance: Company cars | A'ida | October | 2014-10-16 |  | Not yet started
F | GST02 | Stategic: CAPEX | A'ida |  |  |  | Not yet started
F | GST35 | Transitional: Contracts spanning GST start date | A'ida/Faiz |  |  |  | Not yet started

## GST Checklist-PDCC
PDC CONSULTANCY SDN BHD GST WORK PLAN CHECKLIST | [8 empty] | Not yet started
In Progress
Done
Project Lead: James
Category | List of Issues Log |  | PIC | Targeted Month | Target Date | Completed Date | Status | Remarks
A | GST1 | Strategic: Budgeting and Resource Requirement for GST Implementation | James & Mgmt team | August | 2014-08-29 |  | Not yet started
A | GST33 | Transitional: Inclusion of GST clause in all contracts | Rizal / Saari |  |  |  | Done
A | GST3 | Strategic: Preferred vendor management | Mahmudah | September | 2014-09-04 |  | Not yet started
A | GST 4 | Strategic: Price Rebalancing | James & Mgmt team |  |  |  | In Progress
B | GST9 | Compliance: Time of Supply | Sanee |  |  |  | Not yet started
B | GST10 | Compliance: Sale of Tender Documents | Sanee |  |  |  | Not yet started
B | GST11 | Compliance: Advance and Deposit Receipts | James & Sanee |  |  |  | Not yet started
B | GST12 | Compliance: Sundry income and Miscellaneous Expenditure | James & Sanee | September | 2014-09-11 |  | Not yet started
B | GST21 | Compliance: Reimbursement of staff expenses/claims | Mahmudah & Sanee |  |  |  | Not yet started
B | GST22 | Compliance: Goods provided for free | James & Mahmudah |  |  |  | Not yet started
B | GST18 | Compliance: Blocked Input Tax | James & Sanee |  |  |  | Not yet started
B | GST19 | Compliance: Entertainment expenditures | Sanee |  |  |  | Not yet started
B | GST20 | Compliance: Employee Benefits | Mahmudah |  |  |  | Not yet started
E | GST 31 | Compliance: GST Relief for Bad Debts | Sanee | September | 2014-09-18 |  | Not yet started
B | GST 28 | Compliance: Sponsorship | Mahmudah |  |  |  | Not yet started
B | GST29 | Compliance: Payments to Federal & State Governments, Statutory Bodies and Local Authorities | James |  |  |  | Not yet started
B | GST17 | Compliance: Imported services (reverse charge) | <PENDING> | September | 2014-09-25 |  | Not yet started
B | GST13 | Compliance: De minimis and Incidental Financial Supplies | James |  |  |  | Not yet started
B | GST26 | Compliance: Disposal / write off of fixed assets | James & Mahmudah |  |  |  | Not yet started
B | GST30 | Compliance: GST / VAT incurred overseas | <PENDING> |  |  |  | Not yet started
B | GST35 | Compliance: GST on importation of goods | <PENDING> |  |  |  | Not yet started
C | GST14 | Compliance: Apportionment of 'Indirect Costs' for Recovery of Input Tax | James |  |  |  | Not yet started
C | GST24 | Compliance: Inter-Company Supplies and Cross Charges to Related Entities | Sanee | October | 2014-10-02 |  | Not yet started
C | GST25 | Compliance: Open Market Value ("OMV") | James & Sanee & Mahmudah |  |  |  | Not yet started
D | GST5 | Compliance: Tax coding for GST | James & Sanee |  |  |  | Not yet started
D | GST7 | Compliance: Issuance of Tax Invoices | Sanee |  |  |  | Not yet started
D | GST8 | Compliance: GST Adjustments to Tax Invoices with Credit and Debit Notes | Sanee |  |  |  | Not yet started
D | GST16 | Compliance: Accounting recognition vs GST recognition for input tax claim | James & Sanee | October | 2014-10-09 |  | Not yet started
E | GST6 | Compliance: Record keeping requirements for GST purposes | James & Sanee |  |  |  | Not yet started
E | GST23 | Compliance: Reimbursement vs Disbursement | James & Sanee |  |  |  | Not yet started
C | GST15 | Compliance: Documentation to Claim Input Tax Credit | James |  |  |  | Not yet started
E | GST27 | Compliance: Company cars | Mahmudah | October | 2014-10-16 |  | Not yet started
F | GST2 | Strategic: CAPEX | James |  |  |  | Not yet started
F | GST32 | Transitional: Cancellation of PDCC's Service Tax License | Sanee |  |  |  | Not yet started
F | GST34 | Transitional : Contracts spanning GST start date | all |  |  |  | Not yet started

## GST Checklist-IGP
ISLAND GOLF PROPERTIES BERHAD GST WORK PLAN CHECKLIST | [8 empty] | Not yet started
In Progress
Done
Project Lead: <TBC>
Category | List of Issues Log |  | PIC | Targeted Month | Target Date | Completed Date | Status | Remarks
A | GST02 | Strategic: Budgeting and Resource Requirement for GST Implementation | <PENDING> | August | 2014-08-29 |  | Not yet started
A | GST15 | Transitional: Inclusion of GST clause in all contracts | <PENDING> |  |  |  | Not yet started
A | GST04 | Strategic: Preferred vendor management | <PENDING> | September | 2014-09-04 |  | Not yet started
B | GST08 | Compliance: Time of Supply | <PENDING> |  |  |  | Not yet started
B | GST09 | Compliance: Sundry income and Miscellaneous Expenditure | <PENDING> |  | 2014-09-11 |  | Not yet started
B | GST10 | Compliance:De minimis and Incidental Financial Supplies | <PENDING> |  | 2014-09-25 |  | Not yet started
B | GST14 | Compliance: Disposal of fixed assets | <PENDING> |  |  |  | Done
D | GST05 | Compliance: Tax coding for GST | <PENDING> | October | 2014-10-02 |  | Not yet started
D | GST07 | Compliance: Issuance of Tax Invoices | <PENDING> |  |  |  | Not yet started
D | GST12 | Compliance: Accounting recognition vs GST recognition for input tax claim | <PENDING> |  | 2014-10-09 |  | Not yet started
E | GST06 | Compliance: Record keeping requirements for GST purposes | <PENDING> |  |  |  | Not yet started
E | GST11 | Compliance: Documentation to Claim Input Tax Credit | <PENDING>
E | GST13 | Compliance: Reimbursement vs disbursement | <PENDING> |  |  |  | Not yet started
F | GST03 | Strategic: CAPEX | <PENDING> |  | 2014-10-16 |  | Not yet started
F | GST16 | Transitional : Contracts spanning GST start date | <PENDING> |  |  |  | Not yet started
A1 | GST01 | Strategic: Registration for GST | <PENDING> |  |  |  | Not yet started

## GST Checklist-PIHH
PIHH DEVELOPMENT SDN BHD GST WORK PLAN CHECKLIST | [8 empty] | Not yet started
In Progress
Done
Project Lead: Firda
Category | List of Issues Log |  | PIC | Targeted Month | Target Date | Completed Date | Status | Remarks
A | GST02 | Strategic: Budgeting and Resource Requirement for GST Implementation | MS FIRDA | September | 2014-09-04 |  | Not yet started
A | GST04 | Strategic: Preferred vendor management | MR SHAARI |  |  |  | In Progress
B | GST08 | Compliance: Time of Supply | <PENDING> |  |  |  | Done
B | GST09 | Compliance: Advance and Deposit Receipts | MS FIRDA |  |  |  | Not yet started
B | GST10 | Compliance: Miscellaneous Expenditure | <PENDING> |  | 2014-09-11 |  | Not yet started
B | GST16 | Compliance: Blocked Input Tax | <PENDING> |  |  |  | Not yet started
B | GST17 | Compliance: Entertainment expenditures | MS FIRDA |  |  |  | Not yet started
B | GST18 | Compliance: Employee Benefits | MS FIRDA |  |  |  | Not yet started
B | GST19 | Compliance: Reimbursement of staff expenses / claims | <PENDING> |  |  |  | Not yet started
B | GST20 | Compliance: Goods provided for free | MR SHAARI |  |  |  | Not yet started
B | GST21 | Compliance: Free Services | <PENDING> |  |  |  | Not yet started
B | GST23 | Compliance: Sponsorship | <PENDING> |  | 2014-09-18 |  | Not yet started
B | GST24 | Compliance: Payments to Federal & State Governments, Statutory Bodies and Local Authorities | MS FIRDA |  |  |  | Not yet started
B | GST25 | Compliance: GST / VAT incurred overseas | <PENDING> |  | 2014-09-25 |  | Not yet started
B | GST22 | Compliance: Disposal of fixed assets | <PENDING> |  |  |  | Not yet started
B | GST14 | Compliance: GST on importation of goods | <PENDING> |  |  |  | Not yet started
B | GST15 | Compliance: Imported services (reverse charge) | <PENDING> |  |  |  | Not yet started
C | GST11 | Compliance: De minimis and Incidental Financial Supplies | <PENDING> |  |  |  | Not yet started
D | GST05 | Compliance: Tax coding for GST | <PENDING> | October | 2014-10-02 |  | Not yet started
D | GST07 | Compliance: Issuance of Tax Invoices | MS FIRDA |  |  |  | Not yet started
D | GST13 | Compliance: Accounting recognition vs GST recognition for input tax claim | MS FIRDA |  | 2014-10-09 |  | Not yet started
E | GST06 | Compliance: Record keeping requirements for GST purposes | MS FIRDA |  |  |  | Not yet started
E | GST12 | Compliance: Documentation to Claim Input Tax Credit | <PENDING> |  |  |  | Not yet started
F | GST03 | Strategic: CAPEX | MR SHAARI |  | 2014-10-16 |  | Not yet started
A | GST01 | Strategic: Registration for GST | MS FIRDA |  |  |  | Not yet started

## GST Checklist- TELCO
PDC TELECOMMUNICATION SERVICES SDN BHD GST WORK PLAN CHECKLIST | [8 empty] | Not yet started
In Progress
Done
Company : PDC Telecommunication Services Sdn Bhd
Project Lead: Ms Chen
Category | List of Issues Log |  | PIC | Targeted Month | Target Date | Completed Date | Status | Remarks
A | GST01 | Strategic: Budgeting and Resource Requirement for GST Implementation | CHEN/ YANTI | August | 2014-08-29 |  | Not yet started
A | GST31 | Transitional: Inclusion of GST clause in all contracts | FINANCE/SULIANA/ HASMUNIR/ KAMARUL |  |  |  | Not yet started
A | GST03 | Strategic: Preferred vendor management | CHEN/ YANTI | September | 2014-09-04 |  | Not yet started
A | GST04 | Strategic : Price Rebalancing | CHEN/ YANTI |  |  |  | Not yet started
B | GST09 | Compliance: Time of Supply | CHEN/ YANTI |  |  |  | Not yet started
B | GST10 | Compliance: Advance and Deposit Receipts | CHEN/ YANTI |  |  |  | Not yet started
B | GST11 | Compliance: Sundry income and Miscellaneous Expenditure | FINANCE/ SULIANA |  | 2014-09-11 |  | Not yet started
B | GST17 | Compliance: Blocked Input Tax | FINANCE/ SULIANA |  |  |  | Not yet started
B | GST18 | Compliance: Entertainment expenditures | CHEN/ YANTI |  |  |  | Not yet started
B | GST19 | Compliance: Employee Benefits | CHEN/ SULIANA |  |  |  | Not yet started
B | GST20 | Compliance: Reimbursement of staff expenses/claims | CHEN/ SULIANA |  |  |  | Not yet started
B | GST21 | Compliance: Goods provided for free | CHEN/ SULIANA |  |  |  | Not yet started
B | GST28 | Compliance: Sponsorship | FINANCE/ SULIANA |  | 2014-09-18 |  | Not yet started
B | GST29 | Compliance: Payments to Federal & State Governments, Statutory Bodies and Local Authorities | <PENDING> |  |  |  | Not yet started
B | GST25 | Compliance: Penalties, Compensation & Damages Receipts | CHEN/ YANTI |  |  |  | Not yet started
E | GST30 | Compliance: GST Relief for Bad Debts | CHEN/ YANTI |  |  |  | Not yet started
B | GST16 | Compliance: GST on importation of goods | FINANCE/ HASMUNIR/ KAMARUL |  | 2014-09-25 |  | Not yet started
B | GST26 | Compliance: Disposal of fixed assets | FINANCE/ SULIANA |  |  |  | Not yet started
C | GST12 | Compliance: De minimis and Incidental Financial Supplies | CHEN/ YANTI |  |  |  | Not yet started
C | GST13 | Compliance: Apportionment of 'Indirect Costs' for Recovery of Input Tax | CHEN/ YANTI |  |  |  | Not yet started
C | GST23 | Compliance: Inter-company Supplies and Cross Charges to Related Entities | CHEN/ YANTI | October | 2014-10-02 |  | Not yet started
C | GST24 | Compliance: Open Market Value ("OMV") | FINANCE/ SULIANA |  |  |  | Not yet started
D | GST05 | Compliance: Tax coding for GST | CHEN/ YANTI |  |  |  | Not yet started
D | GST07 | Compliance: Issuance of Tax Invoices | CHEN/ YANTI |  |  |  | Not yet started
D | GST08 | Compliance: GST Adjustments to Tax Invoices with Credit and Debit Note | CHEN/ YANTI |  |  |  | Not yet started
D | GST15 | Compliance: Accounting recognition vs GST recognition for input tax claim | CHEN/ YANTI |  | 2014-10-09 |  | Not yet started
E | GST06 | Compliance: Record keeping requirements for GST purposes | CHEN/ YANTI |  |  |  | Not yet started
E | GST14 | Compliance: Documentation to Claim Input Tax Credit | CHEN/ YANTI |  |  |  | Not yet started
E | GST22 | Compliance: Reimbursement vs disbursement | CHEN/ YANTI |  |  |  | Not yet started
E | GST27 | Compliance: Company Cars | FINANCE/ SULIANA |  | 2014-10-16 |  | Not yet started
F | GST02 | Strategic: CAPEX | CHEN/ YANTI |  |  |  | Not yet started
F | GST32 | Transitional : Contracts spanning GST start date | FINANCE/SULIANA/ HASMUNIR/ KAMARUL |  |  |  | Not yet started

## GST Checklist-SU
PDC SETIA URUS SDN BHD GST WORK PLAN CHECKLIST | [8 empty] | Not yet started
In Progress
Done
Company : PDC Setia Urus Sdn Bhd
Project Lead: Doris
Category | List of Issues Log |  | PIC | Targeted Month | Target Date | Completed Date | Status | Remarks
A | GST 01 | Strategic: Budgeting and Resource Requirement for GST Implementation | DORIS | August | 2014-08-29 |  | Not yet started
A | GST 29 | Transitional: Inclusion of GST clause in all contracts | MEIZA |  |  |  | Done
A | GST 03 | Strategic: Preferred vendor management | DORIS | September | 2014-09-04 |  | Not yet started
A | GST 04 | Strategic : Price Rebalancing | DORIS |  |  |  | In Progress
B | GST 09 | Compliance: Time of Supply | DORIS |  |  |  | Not yet started
B | GST 10 | Compliance: Advance and Deposit Receipts | DORIS |  |  |  | Not yet started
B | GST 11 | Compliance: Sundry income and Miscellaneous Expenditure | DORIS |  | 2014-09-11 |  | Not yet started
B | GST 16 | Compliance: Blocked Input Tax | DORIS |  |  |  | Not yet started
B | GST 17 | Compliance: Entertainment expenditures | FADZILAH |  |  |  | Not yet started
B | GST 18 | Compliance: Employee Benefits | FADZILAH |  |  |  | Not yet started
B | GST 20 | Compliance: Goods provided for free | FADZILAH |  |  |  | Not yet started
B | GST 21 | Compliance: Reimbursement of staff expenses/claims | DORIS |  |  |  | Not yet started
B | GST 26 | Compliance: Payments to Federal & State Governments, Statutory Bodies and Local Authorities | MEIZA |  | 2014-09-18 |  | Not yet started
E | GST 27 | Compliance: GST Relief for Bad Debts | MEIZA |  |  |  | Not yet started
B | GST 24 | Compliance: Disposal of fixed assets | DORIS |  | 2014-09-25 |  | Not yet started
C | GST 12 | Compliance: De minimis and Incidental Financial Supplies | DORIS |  |  |  | Not yet started
C | GST 13 | Compliance: Apportionment of 'Indirect Costs' for Recovery of Input Tax | DORIS |  |  |  | Not yet started
C | GST 22 | Compliance: Inter-company Supplies and Cross Charges to Related Entities | DORIS | October | 2014-10-02 |  | Not yet started
C | GST 23 | Compliance: Open Market Value ("OMV") | DORIS |  |  |  | Not yet started
D | GST 05 | Compliance: Tax coding for GST | DORIS |  |  |  | Not yet started
D | GST 07 | Compliance: Issuance of Tax Invoices | DORIS |  |  |  | Not yet started
D | GST 08 | Compliance: GST Adjustments to Tax Invoices with Credit and Debit Notes | DORIS |  |  |  | Not yet started
D | GST 15 | Compliance: Accounting recognition vs GST recognition for input tax claim | DORIS |  | 2014-10-09 |  | Not yet started
E | GST 06 | Compliance: Record keeping requirements for GST purposes | DORIS |  |  |  | Not yet started
E | GST 14 | Compliance: Documentation to Claim Input Tax Credit | DORIS |  |  |  | Not yet started
E | GST 19 | Compliance: Reimbursement vs disbursement | MEIZA |  |  |  | Not yet started
E | GST 25 | Compliance: Company cars | FADZILAH |  | 2014-10-16 |  | Not yet started
F | GST 02 | Strategic: CAPEX | DORIS |  |  |  | Not yet started
F | GST 28 | Transitional: Cancellation of Your Service Tax License | FADZILAH |  |  |  | Not yet started
F | GST 30 | Transitional : Contracts spanning GST start date | DORIS |  |  |  | Not yet started

## GST Checklist-PGT
PENANG GLOBAL TOURISM SDN BHD GST WORK PLAN CHECKLIST | [8 empty] | Not yet started
In Progress
Done
Company : Penang Global Tourism Sdn Bhd
Project Lead: Michelle
Category | List of Issues Log |  | PIC | Targeted Month | Target Date | Completed Date | Status | Remarks
A | GST 02 | Budgeting Resources Requirement for GST Implementation | Michelle | August | 2014-08-29 |  | Not yet started
A | GST 04 | Preferred Vendor Management | Janice, Yani, Jason, Michelle |  | 2014-09-04 |  | Done
A | GST 06 | Price Rebalancing | Michelle |  |  |  | Done
B | GST 10 | Time of Supply | Janice,Michelle |  |  |  | Done
B | GST 12 | Sundy Income and Miscellaneous Expenditure | Janice, Michelle |  | 2014-09-11 |  | Not yet started
B | GST 17 | Blocked Input Tax | Michelle |  |  |  | Not yet started
B | GST 18 | Entertainment Expenditure | Hooi Leng, Jason, Pauline, Michelle |  |  |  | Not yet started
B | GST 19 | Employee Benefits | Hooi Leng, Michelle |  |  |  | Not yet started
B | GST 20 | Reimbursement of staff expenses/claims | Pauline, Jason, Michelle |  |  |  | Not yet started
B | GST 21 | Goods provided for free | Affa, Darren, Michelle, Jason | September |  |  | Not yet started
B | GST 22 | Free services | Michelle, Jason |  |  |  | Not yet started
B | GST 26 | Sponsorship | All Staffs |  | 2014-09-18 |  | Not yet started
B | GST 27 | Payment to Federal & State Governments, Statutory Bodies and Local Authorities | Michelle |  |  |  | Not yet started
B | GST 11 | Commission received | Janice, Michelle |  |  |  | Not yet started
B | GST 28 | GST/VAT Incurred overseas | Yani, Pauline, Michelle |  | 2014-09-25 |  | Not yet started
B | GST 16 | Imported Services (Reverse Charge) | Yani, Pauline, Jason, Michelle |  |  |  | Not yet started
B | GST 23 | Disposal of fixed assets | Michelle |  |  |  | Not yet started
C | GST 13 | De minimis and Incidental Financial Supplies | Michelle |  |  |  | Not yet started
D | GST 07 | Tax Coding for GST | Michelle | October | 2014-10-02 |  | Not yet started
D | GST 09 | Issuance of Tax Invoices | Michelle |  |  |  | Not yet started
D | GST 15 | Accounting Recognition vs GST Recognition for Input Tax Claim | Michelle |  | 2014-10-09 |  | Not yet started
E | GST 08 | Record Keeping requirements for GST purposes | Michelle |  |  |  | Not yet started
E | GST 14 | Documentation to Claim Input Tax Credit | All Staffs |  |  |  | Not yet started
E | GST 24 | GST on Lost/Destroyed/Stolen/Obsolete Stock | Janice, Affa, Evelyn, Michelle |  |  |  | Not yet started
E | GST 25 | Company Cars | Michelle, Hooi Leng |  | 2014-10-16 |  | Not yet started
F | GST 03 | CAPEX | Mr Ooi Chok Yan, Michelle |  |  |  | Not yet started
A1 | GST 01 | Registration for GST | Michelle |  |  |  | Not yet started
A | GST 05 | Approved Tourist Refund Scheme Outlet | Janice, Evelyn, Michelle |  |  |  | Not yet started